DOC-EXEC-21-01-06 Annex 3
# Reporting on the Disability Intergroup Work programme 2020-2022
## Introduction
This document takes stock on the work of the European Parliament Disability Intergroup as per its work programme 2020-2022. If there is any missing activity or you require further information, please write to alejandro.moledo@edf-feph.org.
## Table of contents

## Key events 2020
Agenda	Date	Kind of meeting	Co-organiser	Venue	Update
New year reception	22 January 2020	Open event with EDF	EDF/Ms Langensiepen (Greens)	Brussels, European Parliament (ASP 0G Salon)	Completed
DIG-EDF executive committee meeting	23 January 2020	In camera meeting of proposed members of the Bureau	EDF / Mr Benifei (S&D)	Brussels, European Parliament (ASP 5G305)	Completed
1st Disability Intergroup meeting	13 February 2020	DIG members + EDF	EDF / Ms Maxová (Renew)	Strasbourg, European Parliament (WIC 100 (STR))	Completed
Born accessible (web and media accessibility)	17 March 2020	Public event	Mr Kosa (EPP)	Brussels, European Parliament, Antall building 6Q1	Postponed because of COVID-19 outbreak
Meeting with Commissioner Helena Dalli	April 30	Public event	Commissioner Dalli, EDF and MEPs	Online (+500 participants)	Completed
Meeting of the Disability Intergroup bureau	1 July	Meeting	DIG Bureau members	Online	Completed
Meeting with Commissioner Dalli on Disability Strategy	22 July	Meeting	DIG Bureau members + Commissioner Dalli	Online	Completed
European Disability Strategy	28 October	PETI workshop	PETI secretariat	Brussels, European Parliament	Completed
EDF Board conference “COVID-19 and disability”	30 October	Event	EDF + German DPOs + MEP Langensiepen	Online	Completed
Accessibility Hackathon	30 November	Event	Funka, Facebook, EDF, MEP Kosa	Online	Completed
International Day of Persons with Disabilities	3 December	Action	Disability Intergroup	Online	Completed

# 1. UN CRPD
## UN Convention on the Rights of Persons with Disabilities
The Disability Intergroup helps in the review of the EU by the CRPD committee by hosting expert meetings and reports that shed light on the implementation of the Convention (2021 TBC). The Intergroup can propose to the European Commission to nominate a qualified EU candidate with disabilities for the elections of the CRPD Committee (2020 and subsequent elections).
Nothing to report – EU CRPD review has been postponed.
## European Disability Strategy (Disability Rights Agenda 2020-2030)
The Disability Intergroup leads the way in ensuring that the post-2020 disability strategy is more ambitious that its predecessor, with a foreseen budget for implementation and monitoring, targets to measure its success and the necessary structure to succeed (including a central focal point for the CRPD, focal points in all relevant institutions and agencies and an interinstitutional coordination mechanism), including meaningful involvement of organisations of persons with disabilities and a well-funded Disability Rights Guarantee (2020-2021).
- Oral question tabled by MEPs Estaràs Ferragut, Franssen, Kósa, and Kympouropoulos. Procedure file. Debate in plenary with Commissioner Dalli – 17 December 2019. Resolution on post 2020 Disability Strategy adopted in plenary on 18 June 2020.
- MEP Estaràs participation in the EESC event “Shaping the next Disability Rights Agenda 2020-2030” on 26 February 2020.
- Meeting with Commissioner Dalli on 22 July.
- MEP Agius Saliba written question on the rights of persons with disabilities.
- MEP Maxová written question to the Commission and to the Council on the CRPD focal points, co-signed by 44 MEPs.
## Horizontal Antidiscrimination Directive
The Disability Intergroup keeps urging the Council to agree on an Equal Treatment Directive that protects persons with disabilities from discriminations beyond employment (2020-2021).
Nothing to report.
## Political participation and right to vote
The Disability Intergroup take the lead in promoting Parliament resolution that amends the EU Electoral law from 1976 with the aim of ensuring that in the next European elections in 2024 all persons with disabilities, including those with intellectual and psychosocial disabilities, will be able to exercise their right to vote (2021).
MEP Durant report on stocktaking of European elections adopted on 26 November 2020.
## EP CRPD network
The Disability Intergroup supports the members of the CRPD network and vice versa (2020-2021). The Intergroup can work intensively through this network to argue the creation of a standing Disability Committee.
- Intergroup members who take part in the CRPD Network:
  - Chair (EMPL): MEP Langensiepen. Substitute Al-Sahlani.
  - Members: González (DEVE), Fernandes (BUDG), Kympouropoulos (REGI), Maxová (CULT), Bogdan (LIBE), Estarás Ferragut (FEMM), Kosa and Agius Saliba (PETI). Substitutes: Spurek, Metz, Kanko, Zacharopoulou
- Nothing to report. Due to the COVID-19 outbreak, the CRPD Network has not yet met.
## CRPD independent monitoring framework
The intergroup supports the members of the monitoring framework (from the Committees of Petitions, Civil Liberties and Employment) (2020-2021).
- Intergroup members taking part in the CRPD independent monitoring framework: Kosa, Agius Saliba (PETI), Langensiepen and Al-Sahlani (EMPL), Bogdan (LIBE).
- All resources can be found at the FRA webpage.

## Petitions regarding persons with disabilities rights
The Intergroup is aware of the Petitions sent to the PETI Committee concerning persons with disabilities and follows up when necessary, and pays particular attention to incorrect implementation of the UN CRPD (2020-2021).
- Inclusion Europe petition 0470/2020 on the impact of COVID-19 to persons with intellectual disabilities was discussed at the Petitions Committee on 19 May 2020 and a motion for resolution was adopted in plenary on 8 July 2020.
- Disability Intergroup bureau discussed on 1 July 2020, the following petitions related to the rights of persons with disabilities forwarded by the Petitions Committee:
  - 1077-17 by R. A. (Italian) on the UN Convention on the Rights of Persons with Disabilities
  - 1084-17 by F.G. (Greek) concerning the delay in licensing a public transport vehicle for people with disabilities in the prefecture of Drama (Greece)
  - 0356-18 by Ivan Yanev (Bulgarian) on problems encountered by persons with disabilities in Bulgaria
  - 0367-18 by Arianna Colonello (Italian) on the right to work of persons with disabilities
  - 0724-18 by N. R. (Finnish) on the fundamental rights of people with unacknowledged disabilities
  - 0959-18 by Constantin Vlădescu (Romanian) on denial of health care services for disabled persons in Romania
  - 0773-19 by S.B. (Greek) on supposedly unequal treatment on the base of disability of a family member
  - 0053-20 by Eduardo Prieto Garaita (Spanish) on discrimination against disabled people by the University of the Basque Country
  - 0470-20 Petition on the rights of people with intellectual disabilities in times of covid-19 emergency
- European Union of the Deaf petition submitting petitions in national sign languages. Supported by different Intergroup members in the debate on 14 July 2020.

## Implementation of the CRPD within the Parliament as a public administration
The Intergroup, in collaboration with the disability support groups and the Parliament administration takes steps to make the Parliament inclusive and accessible for employees, guests and elected officials.
- Disability Intergroup bureau letter to the EP Secretary General concerning the accessibility of the multilingual video conference platform and remote voting system sent by MEP Zacharopoulou on 12 May 2020. Response received.
- MEP Durand amendment (116) to the 2021udget of the European Parliament.
- MEP Maxová participation in the virtual meeting of the EP Disability Support Group on 25 June 2020. MEP Langensiepen participation in the EP Disability Support Group meeting on 22 October 2020.
# 2. Mainstreaming Disability Rights
## Disability inclusive response to COVID-19[1]
[1] Item added by the Disability Intergroup secretariat after the COVID-19 outbreak.
The Disability Intergroup works to ensure the rights and health of persons with disabilities is protected during and after the COVID-19 pandemic.
- MEP Langensiepen joint letter with other Green MEPs to Commission President Von der Leyen on 23 March 2020.
- MEP Pagazaurtundúa information on Spain disability inclusive response by Spanish national DPO CERMI on 1 April 2020.
- MEP Cañas written question on flexible measures for autistic people during lockdown.
- Joint letter signed by 47 Disability intergroup members on situation of care and support services of persons with disabilities during the COVID-19 outbreak featured by the EP Magazine. Responded by European Council President.
- MEP Langensiepen written question on the Coronavirus Response Instrument Initiative to protect the rights of persons with disabilities, co-signed by 15 MEPs.
- Disability Intergroup members promoted support to amendments 26, 27 and 58 for EP Resolution on an EU coordinated response to COVID-19.
- Disability Intergroup online meeting with Commissioner for Equality Helena Dalli, and organisations of persons with disabilities: This includes the video, a summary report, and answers to the questions that were not responded during the meeting.
- Following a joint letter of EDF, AGE and EPSU, MEP Majorino along with other MEPs released a statement supporting further investigation on the impact of COVID-19 in residential institutions.
- MEP Langensiepen participation in a webinar about Human Rights violations of persons with disabilities during COVID-19 and a webinar about the recovery plans after COVID-19.
- MEP Benifei written question on COVID-19 vaccination and persons with disabilities.
- MEP Estaràs amendments on the draft report on The gender perspective in the Covid-19 crisis and post-crisis period (2020/2121(INI))
## Data on persons with disabilities
The intergroup works to support the collection of disaggregated data on persons with disabilities, including those living in residential institutions, which can support policy proposals.
- MEP Fragkos written question on data about persons with disabilities co-signed by 13 Intergroup members.
- MEP Kosa written question on inappropriate terminology in Eurostat co-signed by 37 MEPs.
## The next EU budget
The Disability Intergroup members keep track the negotiations concerning the regulations setting up the next EU budget to ensure that it fits for a social purpose, guaranteeing principles of non-discrimination, accessibility and meaningful involvement of representative organisations of persons with disabilities in the use and monitoring of EU funds (2020). The intergroup can adopt a general manifesto about it, and bring the voice of persons with disabilities to regulations such as Horizon Europe, Digital Europe, Creative Europe, Eramus+, Solidarity Corps or InvestEU, NDICI, among others.
- MEP Pislaru and Gusmao work on Recovery and Resilience Facility.
- MEP Langensiepen. Webinar “Cohesion Policy and COVID 19 Recovery and the EU Budget: Influencing the process” – 8 July 2020
## Cohesion Policy and Structural Funds
The Disability Intergroup does everything in its power to ensure that the main Regulations concerning cohesion policy (Common Provisions Regulation, Social Fund + and Regional Development Fund) abide by the CRPD, particularly with regards to non-discrimination, accessibility, forbidding investment in institutional care settings and ensuring the involvement of persons with disabilities and their representative organisations in the governance and monitoring processes (2020-2021).
- Common Provisions Regulations and the European Regional Development Fund have been concluded with members of the Disability Intergroup supporting EDF in the tabling of amendments and approving the reports.
- The European Social Fund+ is still being finalised in the trilogues. We have already seen a strong EP report with the inputs from the disability movement, thanks to the active work of MEPs Benifei and Gusmao (shadow rapporteurs of the ESF+).
## Gender Equality and women with disabilities
The Intergroup promotes a Gender Equality Strategy fully inclusive of women and girls with disabilities, particularly addressing the specific challenges and violations they face (2020-2021).
- MEP Estaràs Ferragut amendments and EMPL opinion to the FEMM report on the EU Strategy for Gender Equality.
- MEP Estaràs Ferragut (FEMM) opinion on the on the implementation of Council Directive 2000/78/EC establishing a general framework for equal treatment in employment and occupation in light of the UNCRPD on 3 December 2020.
- Plenary debate on the EU Gender Equality Strategy: interventions of MEPs Estaràs Ferragut, Spurek on 12 December 2020.

Members of the Intergroup bring the perspective of women and girls in overall work of the Parliament, for example on issues such as poverty, employment, EU in the world and the COVID-19 response.
## Children with disabilities and inclusive education
The Intergroup defends the full inclusion of children with disabilities and the right to access inclusive and accessible education that takes into account their characteristics and needs, including in language immersion education systems. The inclusion of children with disabilities and their families within the Child Guarantee (2020-2021).
- MEPs González, Estaràs and Maite Pagazaurtundua evento on children with disabilities on 3 December 2019.
- MEP Agius Saliba written question on Inclusive education of children with disabilities.
- MEP Maxová written question to the Commission about the EU schools co-signed by 38 MEPs.
- MEP Maxová written question to the Commission about the exclusion of children with disabilities from the PISA tests, co-signed by 20 MEPs.
## EU Green Deal
The Intergroup is instrumental in ensuring that the rights of Persons with disabilities are included in the Green New Deal, including for example a core element of the “renovation wave” for buildings when the programmes are taking more concrete shape (2020-2021).
- MEPs Borzan, Kympouropoulos, Metz and Langensiepen on addressing mobility and accessibility in the building and renovating framework of the European Green Deal on 31 January 2020.
- MEP González amendments on REGI opinion to the Climate Law.
## EU in the world
The Disability Intergroup ensures that the budget focusing on external actions is inclusive pf persons with disabilities transversally and in line with the SDGs. The Disability Intergroup highlights the best examples in which EU external action has a critical role in promoting human rights, inclusion and accessibility for persons with disabilities globally (2020-2021). The Disability Intergroup monitors the implementation of the DG ECHO Operational Guidance on the inclusion of persons with disabilities in EU-funded humanitarian aid operations.
- MEP Zacharopoulou work on EU-Africa strategy
- MEP Al-Sahlani written question on discrimination against Afghan girls with disabilities co-signed by 12 MEPs.

# 3. Social Policies
## Poverty, Social Exclusion and homelessness
The Intergroup promotes action to fight the disproportionate level of poverty and homelessness faced by persons with disabilities in the EU. In light of this worrying trend, the Intergroup will work to support more protective and social policies taking into consideration the extra cost of living that comes from having a disability in a society with multiple barriers (2020-2021).
- MEP Vind report on reducing inequalities with a special focus on in-work poverty.
- MEP Langensiepen amendments to the report on reducing inequalities with a special focus on in-work poverty
- MEP Pislaru EMPL opinion on establishing a Technical Support Instrument.
## Deinstitutionalisation and independent living
The Intergroup supports efforts against institutionalisation of persons with disabilities and showcases best practices regarding independent community-based living and non-coercive measures in mental health (2020-2021).
- MEP González video message on fire in a residential institution in Czechia.
- MEP Gusmao, Matias – GUE support to the study “Lost in interpretation” on use of EU funds in institutionalisation, conducted by ENIL. Webinar to present the study on 9 December 2020.
## EU Pilar of Social Rights
The Intergroup works to ensure accessibility and inclusion within the upcoming action plan on the Pillar, and its implementation (in line with objective 17 “inclusion of persons with disabilities” to live in dignity) (2020-2021). The Intergroup also promotes steps to provide support and advance the inclusion of migrants with disabilities.
Nothing to report.
## Employment
The Disability Intergroup members work to ensure persons with disabilities can access the open labour market with decent work conditions, including a fair minimum wage. The intergroup advocates for EU initiatives in job creation for persons with disabilities. This work can also include actions involving the private sector. (2020-2021).
- MEP Gusmao report on guidelines for the employment policies of Member States.
- MEP Durand video on employment and persons with disabilities.
- MEP Langensiepen report on the implementation of Council Directive 2000/78/EC establishing a general framework for equal treatment in employment and occupation in light of the UNCRPD with an explanation in easy-to-read format.
- MEP Agius Saliba written question on Quality employment for persons with disabilities.
# 4. Accessibility & free movement
## Accessibility and assistive technologies
The Disability Intergroup is instrumental to keep advancing on legislation incorporating accessibility as a pre-requisite. Domains in which the Intergroup could work are:
- accessibility to the built environment and housing,
- accessibility of transport services
- accessible ICT (web, telecommunications, media) – digital technologies
- accessible health care services,
- accessibility in culture,
- assistive technologies

- MEP Van Sparrantak report on Access to decent and affordable housing for all.
- MEP Agius Saliba written question on Subtitles for deaf and hard of hearing and taxi services for persons with disabilities.
- MEP Benifei dissemination of RDDA project (EC Publications Office).
- MEP Zacharopoulou opinion onf the EU4Health Programme.
- MEP Kosa participation as jury member in the first Accessibility Hackathon in Europe, organised by Funka and Facebook, on 30 November.
- MEP Alieva Veli jury member of the EDF-Oracle e-Accessibility scholarship.
- MEP Agius Saliba written question to create the EU Access Board, co-signed by 39 MEPs.
## Artificial Intelligence and other emerging technologies
The Intergroup defends an inclusive approach to Artificial Intelligence (AI) respecting accessibility, mobility and non-discrimination of persons with disabilities. The Intergroup will liaise with the special EP Committee on AI and promotes specific investment plans for the research and application of inclusive algorithms taking into account human diversity.
Nothing to report.
## Passengers’ Rights
Currently, the Rail Passengers’ Rights Regulation is in trilogues (2020). The Intergroup advocates for a strong EP position in the negotiations. Furthermore, the Intergroup pushes the Commission to revise the Air Passengers’ Rights Regulation (2021).
- Joint letter signed by 43 MEPs on Rail Passengers Rights negotiations.
- MEP Cañas written question on air passengers rights for persons with disabilities.
## EU Disability Card
The Intergroup keeps encouraging the Commission invest the resources to extend the pilot project of the Disability Card to all Member States paving the way for a mutual recognition of disability rights across the EU (2020-2021).
- MEP Langensiepen written question on the EU Disability Card, co-signed by 19 MEPs.
- MEP Gemma written question on the EU Parking Card.
- MEP Cañas written question on the EU Disability Card.
# 5. Raising awareness and collaboration
## Visibility of the rights of persons with disabilities and of the Disability Intergroup
The Disability Intergroup members promote through different communication channels the rights of persons with disabilities and the work of the Intergroup.
- Renew Europe’s Group commitments to ensure the rights of persons with disabilities.
- MEP González video on 3rd December 2020 on the international day of persons with disabilities promoted on social media.
- MEP Zacharopoulou featured in the EP Magazine.
- MEP Maxová campaign on focal points on 3rd December 2020.
- Disability Intergroup statement on the International Day of Persons with Disabilities, translated in several languages, featured in the EP Magazine.
## Collaboration with the Commission
The intergroup maintains regular exchanges with Commissioner for Equality, Helena Dalli, and with the Commission’s Disability and Inclusion unit.
- Public online event with Commissioner Dalli on the impact of COVID-19 on persons with disabilities on 30 April 2020. Over 500 participants registered.
- Meeting of the Disability Intergroup bureau with Commissioner Dalli on the post 2020 Disability Strategy on 22 July 2020.
- MEP Langensiepen written question on the Commission Task Force on Equality, co-signed by 37 MEPs.
## 5th European Parliament of Persons with Disabilities
The Disability Intergroup members are central in the organisation of the 5th European Parliament of Persons with Disabilities to be organised in 2020 or beginning of 2021 to support the participation of persons with disabilities across the EU, get the political support of their groups as well as the President and administration of the Parliament. Given the preparation of the next Disability Strategy and the high number of new MEPs, having the EPPD as soon as possible is a political opportunity.
Nothing to report.
## Visibility and raising awareness of specific disabilities
The intergroup works to raise awareness among other EU policy makers and the general public of the specific needs of the diverse community of persons with disabilities, e.g. deafblindness, intellectual and learning disabilities, mental health issues, etc.
- MEP Gemma expert meetings about autism – July 14th with Autism Europe, EDF and Italian organisations and experts on autism.
- MEP Metz ambassador of Multiple Sclerosis.
- Written question on an EU mental health strategy, co-signed by 6 MEPs.
- MEP Kympouropoulos written question on employability and rare diseases, co-signed by 25 MEPs.
## Meaningful involvement of persons with disabilities through their organisations
Intergroup members maximise the opportunities for organisations of persons with disabilities to address the Parliament and the Disability Intergroup to explain their priorities (2020-2021).
- Round of meetings with MEP Langensiepen with different disability organisations for preparing the report on the implementation of Council Directive 2000/78/EC establishing a general framework for equal treatment in employment and occupation in light of the UNCRPD.
- MEP Pelletier meeting with disability organisations on 4th February 2020.
- MEP Homs with EUD inclusion of sign language in the European charter for minoritarian and regional languages.
## Collaboration with other equality intergroups and the Disability Support Group of the European Parliament
The Disability Intergroup regularly collaborates with other human rights based intergroups of the Parliament, as well as with the Disability Support Group formed by EP staff with disabilities (2021-2022). For example, on poverty, social exclusion and homelessness, the Intergroup can contact the "Fighting against poverty"-intergroup to join forces, or for accessibility, assistive technologies and other emerging technologies, the Intergroup can liaise with the "Artificial Intelligence and Digital" intergroup.
MEP Langensiepen participated in the LGTBI Intergroup online event on Lesbian Visibility Day.
Letter with other equality intergroups to the PM of North Macedonia about the national antidiscrimination law.
# Contact
Disability Intergroup secretariat:
Alejandro Moledo, alejandro.moledo@edf-feph.org, +32 486 741 508