[image: image1.jpg]Funded by
the European Union




[image: image2.png]EUROPEAN
DISABILITY

FORUM






DOC-EXEC-21-09-03
                         Update on EDF involvement in projects
                                   Document for information and decision
Table of Contents
2Introduction and purpose


2Decisions for the executive:


2New project: Strengthening the Disability Movement in Central and Eastern Europe


4Annex: Ongoing projects which do not require decisions


4B-WISE (Blueprint for Sectoral Cooperation on Skills in Work Integration Social Enterprises)


5Inclusive Universities for all- (EUUni4All)


6The 25% Project Conference on the future of Europe- Youth Forum


7Strengthening resilience of older persons and persons with disabilities during COVID-19 and future disasters (CovidResilience, RESOPP)


9European Disability Expertise


10Web Accessibility Initiative-Communities of Practice (WAI-COOP)


11Inclusive Mobility Alliance 2.0 (IMA)


11Technical Assistance in Humanitarian Response (VIVID:T)


12Disability Advocacy Research in Europe (DARE)


13Building Partnerships for the SDGs - Empowering Indian DPOs


14Innovation to Inclusion (i2i)


15Disability Hub Europe for Sustainable Growth and Social Innovation (DHub)


16D-WISE (formerly the European Observatory for Inclusive Employment and Sustainable Development Goals: ONCE Foundation)


16Finalised projects


16JUSTforALL


17WHO Europe - Inclusive and accessible public health messages about COVID-19


17Mapping disability inclusiveness


18Bridging the Gap II


18Promoting Disability Inclusive International Cooperation




Introduction and purpose

This document outlines EDF’s current projects, some new projects in the inception period and some project applications and rejected projects. Following the advice from our Treasurer at the last executive, each project is presented systematically with the same information provided for each. 

Decisions for the executive: 
For the project- Strengthening the Disability Movement in Central and Eastern Europe, our Board member Branislav Mamojka wll be involved. Would any additional Executive member like to be a focal point for this capacity building project?
New project: Strengthening the Disability Movement in Central and Eastern Europe
· Title: Strengthening the Disability Movement in Central and Eastern Europe
· Donor and timeframe: CITI Foundation – 12 months from October 2021 to October 2022
· Total budgets: $250,000.00
· Objective of the project: The project aims to build capacity of 5 EDF members, and all activities will be done in partnership with them in each country, in Central and Eastern Europe. 

Main objectives: 
· Strengthening communication with members and individuals
· Capacity building in EU and international policies and programmes 

· Capacity building in the field of youth leadership and opportunities  
· Partners: National Council of People with Disabilities in Bulgaria, Czech National Disability Council, Hungarian National Council of Federations of People with Disabilities, Romanian National Disability Council (CNDR), Slovak disability council (NROZP v SR, Narodna rada obcanov so zdravotnym postihnutim v SR)
· EDF role: EDF plays a role in promoting learning and development within the disability movement in Europe and uses all opportunities to build the capacity of the movement.  EDF provides tools and training on a range of subjects for 5 members associations in order to strengthen their advocacy work at the national and local level.

· EDF staff & executive member(s) involved: ongoing 
· Current activities, foreseen outcomes, successes (if any worth noting): The project is not started yet
· Questions for the executive: Who would like to be focal point for this project?

Annex: Ongoing projects which do not require decisions 
For each project, the following information is required within a one page limit: 
· Title (including link to our web page)
· Donor and timeframe

· Total budget and EDF budget

· Objective of the project

· Partners (if any)

· EDF role 
· EDF staff & executive member(s) involved

· Current activities, foreseen outcomes, successes (if any worth noting)
B-WISE (Blueprint for Sectoral Cooperation on Skills in Work Integration Social Enterprises)

· Title: B-wise - Blueprint for Sectoral Cooperation on Skills in Work Integration Social Enterprises
· Donor and timeframe: European Commission ERASMUS+ co-funded
· Total budget and EDF budget: No EDF budget
· Objective of the project: 

The B-WISE project aims to develop and implement a new strategic approach (Blueprint) to sectoral cooperation on skills needed in order to:

· Reinforce the empowering work of Work Integration Social Enterprises (WISEs);

· Strengthen the skills and competences of disadvantaged groups but also supporters (tutors, job coachers…) and managers;

· Sustainably tackle the digital gap and digital challenges the sector faces.
· Partners: ENSIE, EASPD
· EDF role: To serve in the Advisory Board of the B-WISE project
· EDF staff & executive member(s) involved: Farbod Khasari, Haydn Hammersley
· Current activities, foreseen outcomes, successes: Project launch conference on 14th October
Inclusive Universities for all- (EUUni4All)

· Title: Inclusive University for all – EUUniAll 
· Donor and timeframe: This project is Funded by Erasmus+ Programme and coordinated by Fundacion ONCE, EDF member. The project started on November 1st 2019 – March (timing extended due to Pandemic situation) 31st 2021 a total of 26 months
· Total budget 290.530,00€ and EDF budget 44.240,00: 

· Objectives of the project: 

· Encourage the inclusion of persons with disabilities in higher education through diagnosis and analysis of inclusive universities to be a reference for other universities.

· Create a network of inclusive universities to reduce the barriers for persons with disabilities to higher education, as well as to equate the strategies of universal accessibility for all.

· Promote the inclusion in the university community supporting both faculty and administrative staff in order to stimulate diversity.

· Promote the international mobility among the students with disabilities and raise awareness within the university community regarding accessibility and social inclusion of young persons with disabilities.

· Partners (if any): Lead: ONCE Foundation for the inclusion of people with disabilities in Spain. Partners: University of Eastern Finland the University of the Study of Trieste (Italy) the Polytechnic University of Lublin (Poland) the University of Porto (Portugal), Universities of Murcia, Autonomous University of Madrid, University of Seville. Learn more about the partners.
· EDF role: 

· Give input on developing the standards for inclusive universities

· Coordinate the development of a training that will provide to faculty members and administrative staff from different EU countries information and awareness on disability inclusion 

· Participate in the project activities

· Organise the final meeting and multiplier event in March 2022
· Dissemination of activities and materials
· EDF staff & executive member(s) involved: Albert Prévos, Loredana Dicsi, Muriel Davia for finance and admin An-Sofie Leenknecht & development of the training. Natalia Suarez, Roberta Lulli for development of guide for trainers and other visuals.
· Current activities, foreseen outcomes, successes (if any worth noting). 
· Developing the Training

· A public Meeting Hosted by University of Porto in November
· Testing of the developed standards by Universities

The 25% Project Conference on the future of Europe- Youth Forum 

· Title: The 25% Project and The 25% on EDF Website
· Donor and timeframe: This project is led by Youth Forum and funded by the European Parliament. It is from 1 February 2021 and 30 June 2022.
· Total budget and EDF budget: 10 000 total for all activities, staff, etc
· Objective of the project: 

· Create a new movement where the unheared 25% can be heared.
· Make aware and inform young people on the Conference on the Future of Europe

· Create a toolkit that helps young people to make change

· Empower young people to bring change being trained by peers.

· Collect ideas from young people for a better europe to feed in the Conference on the Future of Europe.
· Partners (if any):
· 5 National Youth Council
· 5 European NGOs, mostly Youth Organisations

· 1 Research Center
· 1 Outreach Organisation
· EDF role: 

· Attend and engage with monthly Consortium meetings held either in person or virtually.

· Ensure the project is inclusive and accessible for youth with disabilities 

· Encourage local and national partners or members to organise local events that collect at least 1,400 ideas.

· Encourage and promote the project and the online platform through communications channels and networks.

· Promote the outcomes of the project and interested decision makers.

· Send at least 3 participants to the European Youth Event.

· Send at least 10 participants to the international event in Brussels.
· EDF staff & executive member(s) involved: Loredana Dicsi, and Youth Committee, Muriel Davia for finance and admin. 
· Current activities, foreseen outcomes, successes (if any worth noting). 
· Workshop given by EDF Youth Committee to youth within the membership (sept/october to be decided)
· Participation in the European Youth Event and bringing input in the ones organised within the framework of the project. 8-10 October 2021.
· Collecting ideas from young people or from thoswe working with them or interested in them until November 2021, ongoing.
· Question for the Executive
Who would like to follow up on this project? (the person following up on the Conference on the Future of Europe, or one of the focal points for the Youth committee?)
Strengthening resilience of older persons and persons with disabilities during COVID-19 and future disasters (CovidResilience, RESOPP)

· Donor and timeframe: This project is funded November 2020-November 2023 (36 months)
· Total budget and EDF budget: 19 000 total for all activities, staff, etc (37 staff days over the course of the action)
· Objective of the project is to contribute to strengthened resilience of older persons and persons with disabilities in the Western Balkans during Covid-19 and future disasters 
· Specific objective: Older persons, persons with disabilities, CSOs and grassroots organisations are better able to cope with the Covid-19 situation in Albania, Bosnia and Herzegovina, North Macedonia, Montenegro, Serbia and Kosovo
· Partners: Leader- Red Cross Red Cross of Serbia (Main applicant, project coordination),  Austrian Red Cross (Technical support, CVA capacity development lead),  AGE Platform Europe (designing and delivering two training cycles to representatives of the five national CSO networks, contributing to the development and dissemination of public policy proposals),  European Disability Forum (designing and delivering two training cycles to representatives of the five national CSO networks, contributing to the development and dissemination of public policy proposals)  SeConS Development Initiative Group. Albanian Red Cross,  Albanian Association of Geriatry and Gerontology (AAGG) ,  Red Cross Society of Bosnia and Herzegovina,  Association for Help and Development HAJDE, Bosnia and Herzegovina,  Red Cross of Montenegro,  Association of Blind Persons Montenegro ,  Red Cross of North Macedonia ,  Humanost NGO, North Macedonia, Caritas Kosova, National Organisation of Persons with Disability Serbia (NOOIS) 
· EDF role: Contribute to training cycles, which are led by Age Platform- EDF experts give input in trainings on the CRPD and rights of persons with disabilities
· EDF staff & executive member(s) involved: An Sofie for the technical input and Muriel Davia for reporting. Executive members perhaps for trainings at a later date as required.
· Current activities, foreseen outcomes, successes (if any worth noting). 

· There are not important activities for EDF at this point except organising the contract, defining roles and responsibilities.
European Disability Expertise 
· Title: European Disability Expertise 
· Donor and timeframe: European Commission DG EMPL - Maximum 3 years
· Total budget and EDF budget: Estimated total value excluding VAT of 2.14€ million for the first 18 months. EDF Budget of 6000€ for 7.5 days work in the first 18 months.
· Objective of the project: This is a continuation of the Academic Network of European Disability Experts (ANED). It will see research conducted by national experts in each Member State on a number of thematic areas (see section below for list of topics). These will then be presented on an openly accessible website, and complemented by analysis from Senior experts.
· Partners (if any): Lead: Human European Consultancy. Senior experts for research will be Mark Priestley (University of Leeds), Lisa Waddington (University of Maastricht), Anna Lawson,  Paula Campos Pinto, Magdi Birtha (European Centre for Social Welfare Policy and Research), Christian Bohler (European Centre for Social Welfare Policy and Research), Andrea Broderick (Maasticht University), Ines Bulic Cojocariu (ENIL), Neil Crowther, Gauthier de Beco (University of Huddersfield), Delia Ferri (Maynooth University), Hannah Grene, Christopher Hatton (Centre for Disability Research, UK), Gerard Quinn, Nadia Hadad, Elizabeth Mestheneos (Age Platform Europe). There will also be one national expert per EU Member State.
· EDF role: Nadia Hadad from EDF will act as one of the senior experts reviewing the research into the implementation of the Sustainable Development Goals at a national and EU level from a disability perspective.
· EDF staff & executive member(s) involved: Nadia Hadad and Haydn Hammersley
· Current activities, foreseen outcomes, successes (if any worth noting): Report on COVID-19 response in the Member States completed, research on new technologies and finalisation of the report is ongoing, research on the European Semester and its impact on persons with disabilities is beginning, and the creation of the new online platform for accessing the research papers and reports is underway.
Web Accessibility Initiative-Communities of Practice (WAI-COOP)
· Title: WAI-CooP: Web Accessibility Initiative, Communities of Practice
· A webpage on the project is currently on the W3C website we will launch a dedicated EDF webpage with the FAQs website as soon as it is ready.
· Donor: EC Horizon 2020
· Timeframe 36 months 01/01/2021-31/12/2023
· Total budget and EDF budget- total budget- Total budget is 1,499,987.50, EDF budget: one full time senior staff member – Carine Marzin
· Objective of the project: 
· To set up a digital accessibility observatory as a forum to take stock of market and technological developments, monitor progress in digital accessibility and provide opportunities for exchange. 
· Establish vendor-neutral overview on available training, tools, and resources internationally

· Analyse technological advancements and coordinate with relevant research and development

· Provide opportunities for key stakeholders to share resources and exchange best practices

· Partners (if any): W3C-ICT, HAN University of Applied Science NL, FCIENCIAS.ID - ASSOCIACAO PARA A INVESTIGACAO E DESENVOLVIMENTO DE CIENCIAS Portugal, DEQUE RESEARCH BV
· EDF role: ensure DPO involvement in implementation of directive, ensure stakeholder engagement and build capacity with a helpdesk and curated Frequently Asked Questions (FAQs). 
· EDF staff involved: Management- Coordination: Alejandro Moledo, Carine Marzin (from January 2021). 
· EDF executive member(s) involved: Maureen Piggot
· Current activities and priorities in the project: a First Open meeting took place online on 23 June 2021 with 150+ registrations; work on the FAQs for the dedicated website has been completed and the website will be launched once the technical set up for the helpdesk contact form has been finalised. We are now preparing for our second open meeting – date and themes to be confirmed shortly.
· Foreseen outcomes: EDF’s key deliverables focus on the promotion and exchange of best practice with the following activities
· Hold Regular Open Meetings to promote the involvement of people with disabilities in implementation and monitoring efforts

· Manage Help Desk to respond to questions from stakeholders on implementing the EU Web Accessibility Directive (WAD)

· Curate Frequently Asked Questions (FAQs) on the EU Web Accessibility Directive (WAD)

These deliverables will be complemented by dissemination and engagement efforts.
· Successes till now: project started 1 January 2021; a well-attended and well received first open meeting on 23/06/21 and FAQs content ready for imminent website launch. One partner moved jobs but 
· Possible risks: open meetings were intended as face-to-face but will continue online for now due to COVID
· Decisions for the executive: N/A 
Inclusive Mobility Alliance 2.0 (IMA)
· Title: Inclusive Mobility Alliance 2.0 (IMA)
· Inclusive Mobility Alliance 2.0 on EDF website
· EDF staff involved: Loredana and Kamil Goungor
· Total budget: There is currently no funding for this project, but the partners continue to meet to collaborate.
· Current activities, foreseen outcomes, successes (if any worth noting)

· The Alliance will meet again in the second half of the year, date to be established. EDF will participate as the executive decided to remain part of this process. There are no questions at this stage for the Executive Committee. 
Technical Assistance in Humanitarian Response (VIVID:T)
· Title:  VIVID:T (Technical Assistance in Humanitarian Response, Ensuring Valuable International Volunteering and Inclusion of persons with Disabilities)

· Link to our webpage: https://www.edf-feph.org/projects/vividt/
· Donor and timeframe: Funded by ECHO and managed by EACEA; February 2020 to January 2022 (24 months)
· Total budget and EDF’s budget: €1,000,000.00; EDF’s budget: €170 000 
· Objective of the project: Contributes towards improving the capacity of the European Union to provide humanitarian aid. 

· Partners: CBM Ireland as lead, EDF, Tearfund Ireland, Viatores Christi, ASPEm Italy, CBM Germany and CBM International 
· EDF role: improves the capacity of EU organisations to develop and oversee humanitarian projects and to deploy EU Aid volunteers.
· EDF staff and executive members involved: 
· Marion Steff: International Cooperation Manager

· Diana Zsoldos: Communications and Logistics Officer for International Cooperation
· Roberta Lulli: Digital Accessibility Trainer for VIVID-T
· Catherine Naughton (in steering committee)
· Gunta Anca: Secretary, EDF executive member
· Nadia Hadad: EDF executive member
· Current activities, foreseen outcomes, successes (if any worth noting): The project becomes a model for EU to support volunteer agreement to include disability activities in volunteering.
Disability Advocacy Research in Europe (DARE)
· Donor: European Commission, Research Institute Agency

· Timeframe: 1/1/2019-30/9/2022 and Budget: €4,120,264.80 
· Objective of the project: to train the new generation of researchers in the field of disability rights, by embedding them in the top universities in this field, with exposure to key civil society organisations working at grassroots level to secure the rights of persons with disabilities.

· Beneficiaries and partners: National University of Ireland Galway, EASPD, EDF, University of Leeds, Maastricht University, Swiss Paraplegic Institute, University of Iceland, Institute of Political and Social Sciences, Special Rapporteur on the Rights of Persons with Disabilities, International Foundation of Electoral Systems, Pi Consultancy NL LLP, Lumos Foundation, AGE Platform Europe, CBM, European Association of Palliative Care, Inclusive Research Network, European Social Network, Justice, Vision Sense.

· EDF role: EDF hosts Aoife Price for three years and supports her in her research project on ‘combining voices: coalition building and alliances with other social movements’. She focuses on how disability civil society organisations interact constructively with the women’s rights movements in driving forward a programme of change. She supports EDFs work of the Women’s Committee, our cooperation with EWL and any other relevant gender equality and human rights work. She undertook in the fall of 2020 a secondment with the European Women’s Lobby. She will take a secondment with NUI Galway in September 2021. EDF also hosted Claudia Coveney for a secondment placement in fall 2020. Claudia is studying the history of the disability movement within Europe and is working with Loredana and Muriel to reach out to EDF members and people to gather data. 
· EDF staff and Executive Committee members involved: Catherine Naughton, An Sofie Leenknecht, Muriel Davia, Aoife Price, Pat Clarke, Pirkko Mahlamäki and Ana Pelaez. 
· Current activities and priorities in the project:  Aoife is currently transcribing the interviews for her research, starting to draft her PhD and completing her secondment with NUI Galway. An-Sofie started organising the final training event together with Maastricht University and Lisa Waddington. The training event will take place in the Spring of 2022. 
Building Partnerships for the SDGs - Empowering Indian DPOs
· Title: Building Partnerships for the SDGs - Empowering Indian DPOs.
· Donor and timeframe: EEAS India; March 2018 – March 2021 (three years). New extension to December 2021. 
· Total budget and EDF budget: 350 000 Euros; EDF budget’s: 81 342 Euros

· Objective of the project: Women and men with disabilities engage in, shape and monitor the implementation of the SDGs in India. Specific objective: Establish, strengthen and stimulate policy dialogue and partnership between DPOs in India and EDF.  

· Partners (if any): Sightsavers and EDF
· EDF role: Ensure that strong partnerships are developed between DPOs in India and EDF. The anticipated impact will be both an increased awareness within EU countries of global disability policies and (in the spirit of follow up and review) opportunities to learn from one another on what works in different context for disability inclusive implementation of the 2030 Agenda and the SDGs. 

· EDF staff and EDF executive members involved: 
· Marion Steff: International Cooperation Manager  
· Diana Zsoldos: Communications and Logistics Officer for International Cooperation
· John Patrick Clarke: EDF’s Vice President 

· Nadia Hadad: Executive member
· Current activities, foreseen outcomes, successes (if any worth noting): Completion and online dissemination of “ Rising Voices” - A joint paper on Mainstreaming Women with Disabilities in India-EU international cooperation and SDG Implementation; Initial discussions have been started with a DPO of Jharkhand and EDF for future collaboration and developing a formal agreement among the two.
Innovation to Inclusion (i2i)
· Title: Innovation to Inclusion (i2i)
· Innovation to Inclusion on EDF webpage
· Donor and timeframe: UK FCDO, July 2018 to March 2022 
· Total budget and EDF budget: 9 million pounds; for EDF, 400 000 Pounds

· Objective of the project: The programme addresses barriers to employment within the Private Sector in Kenya and Bangladesh. 
· Partners (if any): Bangladesh Business and Disability Network; Action for the Disabled Network Kenya; CBM; Benetech; London School of Hygiene and Tropical Medicine; Plan International UK; ILO; WB and EDF  
· EDF role: National Systems and Policies support enabling environments for equal access to private sector employment for women and men with disabilities

· EDF staff and executive members involved: Marion Steff, Catherine Naughton, Gordon Rattray, An-Sofie Leenknecht & Maureen Piggot
· Current activities, foreseen outcomes, successes (if any worth noting)

Successes so far include: supporting DPOs in data gathering around CRPD articles 27 and 28; completion of workshops with DPOs in Kenya and Bangladesh developing advocacy strategies; production of COVID-19 influence pack. Current work includes: production of several resource documents in accessible format; follow-up of advocacy strategy; and, supporting DPOs from both countries to participate in COSP and Work Forum 2021. Foreseen outcome is improved access to formal employment for persons with disabilities (including women with disabilities) through data-driven advocacy in Kenya and Bangladesh, and their increased meaningful participation in decision-making processes around these topics.
Disability Hub Europe for Sustainable Growth and Social Innovation (DHub)

· Title: Disability Hub Europe for Sustainable Growth and Social Innovation (DHub)
· Donor and timeframe: Fundación ONCE and co-funded by the European Social Fund - 2018 to 2020 – Now extended to 2023
· Total budget and EDF budget: No budget for EDF.
· Objective of the project: Aligned with the Agenda 2030 and the Sustainable Development Goals, the final goal of DHub is to foster social and labour inclusion of people with disabilities in Europe while promoting inclusive and sustainable business.
· Partners (if any): Fundación ONCE, EDF, L'Oréal, Global Reporting Initiative, CSR Europe, Forética, Flemish Government Department for Work and Social Economy, European Foundation Centre and the ILO Global Business and Disability Network. 
· EDF role: Disseminating DHub activities and results through EDF communication channels; contributing and supporting policy incidence actions carried out in the framework of DHub related to sustainability, providing speakers for events and webinars.

· EDF staff & executive member(s) involved: Haydn Hammersley

· Current activities, foreseen outcomes, successes (if any worth noting): Enhanced understanding of different ways persons with disabilities can be included in the open labour market; Archive of innovative and effective approaches to fostering quality employment for persons with disabilities in the open labour market; stronger links between inclusive employers and adoption of good practices by businesses hoping to become more inclusive; Project mentioned in the outcome document of the Regional Forum for Sustainable Development.  
D-WISE (formerly the European Observatory for Inclusive Employment and Sustainable Development Goals: ONCE Foundation)

· Title: D-Wise Network 
· Donor and timeframe: ONCE Foundation, European Platform for Rehabilitation, and EASPD – 2018-2020 - Now extended to 2022
· Total budget and EDF budget: Once Foundation 120.000. No resources for EDF.
· Objective of the project: Enhancing the understanding of social inclusive companies in Europe employing a significant percentage of persons with disabilities.
· Partners (if any): Once Foundation, European Platform for Rehabilitation, and EASPD

· EDF role: EDF acts as an observer and was expected to: Attending meetings (quarterly basis), Supporting the Project and contributing with relevant knowledge and expertise, Contribution to papers/recommendations. 
· EDF staff & executive member(s) involved: Haydn Hammersley
· Current activities, foreseen outcomes, successes (if any worth noting): Forming a strategic partnership to face the challenges and opportunities of social inclusive employment for persons with disabilities in Europe; Research on the different employment schemes and mechanisms for people with disabilities in the different countries and analysis of their compliance with the CRPD.
Finalised projects

JUSTforALL 

· Title: JUSTforALL 

· JUSTforAll on EDF webpage 
· Donor and timeframe: European Commission, DG Justice and Consumers. 30 months – from 01 Oct 2018 to March 2021
· Total budget and EDF budget: 459.641,33 and 48.594 EURO (6 months staff costs included)
· Objective of the project: JUSTforALL promoted full access to justice for persons with disabilities through the training of legal practitioners. 

WHO Europe - Inclusive and accessible public health messages about COVID-19
· Title: Inclusive and accessible public health messages about COVID-19

· Project link to our webpage
· Donor and timeframe: WHO Europe; September to January 2021

· EDF budget: 30 000 Euros
· Objective of the project: Make key WHO public health messages more accessible to persons with disabilities, using the urgency of the COVID-19 pandemic as an opportunity to install this vital feature into all communications as the norm. EDF developed a series of materials focusing on the inclusion of persons with disabilities in response to COVID-19, including  COVID19 prevention, access to health services, and rehabilitation. 

· Create survey of EDF members to identify specific issues to be addressed in the videos as well as good practices. 
· Produce a guidance note on the needs and best practices related to persons with disabilities in COVID-19 public health communication in the WHO European region. 

· Identify couple of good practice examples from countries which can be posted as a WHO-EDF web news. 

· Create two videos converting WHO public health messages on disability and COVID-19 into formats accessible to those with disabilities. They will be informative but also used to inform as to good practices for public health departments. 

Mapping disability inclusiveness

· Title (including link to our web page): Mapping disability inclusiveness of European member states’ development and humanitarian aid

· 
Donor and timeframe: Summer 2020-Spring 2021

· Total budget and EDF budget: 

· Objective of the project: to assess the extent to which European Member States’ development aid official development aid is inclusive of and accessible to persons with disabilities.

· Current activities, foreseen outcomes, successes (if any worth noting): 'Fact sheet' about disability inclusiveness in development aid are being developed for the European Union as well as the Denmark, Finland, Germany, Ireland, Italy, Norway, Spain, Sweden and the United Kingdom. 

 Bridging the Gap II

· Title:  Bridging the Gap II – Inclusive Policies and Services for Equal Rights of Persons with Disabilities
· Bridging the Gap II on EDF webpage 
· Donor and timeframe: DEVCO; April 2017 to April 2021 (4 years). Extended until August 2021. 

· Total budget and EDF budget: 6 800 000 €. The project budget for implementation by EDF and IDDC is 492 920 Euros (+ 24 646 Euros of administrative fees). IDDCmanages the budget allocated to IDDC and EDF. EDF does not benefit or contribute financially to the project, providing simply expertise (EDF could not at the time of project planning commit to co-financing). 

· Objective of the project: The project aims to contribute to the socio-economic inclusion, equality and non-discrimination of persons with disabilities in Ecuador, Paraguay, Burkina Faso, Sudan and Ethiopia.

· EDF role: EDF brings to the project its thematic expertise and experience in the field of disability and SDGs, ensuring that the content of the CRPD is properly addressed and respected in all phases of the project implementation.
Promoting Disability Inclusive International Cooperation 
· Title: Promoting Disability Inclusive International Cooperation
· Link of the project on EDF webpage
· Donor and timeframe: Wellspring Philanthropic Trust; October 2019 – August 2021 (2 years)
· Total budget and EDF budget: US $400 000

· Objective of the project: The EU becomes a global leader in disability inclusive development, with DPOs actively and meaningfully involved in international cooperation.

· EDF role: Implementing the project

· EDF staff and executive members involved: Marion Steff, Gordon Rattray, Diana Zsoldos, An-Sofie Leenknecht; John Patrick Clarke and Nadia Hadad
· Current activities, foreseen outcomes, successes: This project supports all the implementing work of the international team. 

[image: image3.jpg]Avenue des Arts 7-8 Tel+3223290059 info@edf-feph.org
B1210 Brussels - Belgium Fax+322329 0059 www.edf-feph.org



3

