ANNEX I DOC-EXEC-23-01-07

# EDF 2023 Work Plan

EDF’s annual Work Plan for 2023 is divided into 5 Work Packages and has 15 deliverables in total. The focus is on implementation of the UN Convention on the Rights of Persons with Disabilities (CRPD), the implementation of the European Strategy on the Rights of Persons with Disabilities (ESRPD) and capacity building and training of EDF’s membership on national and EU level. Management of the network and communication and dissemination of EDF’s work is of course also included. All activities include persons with disabilities in their full diversity

Work Packages

Work Package 1: General management and running of the organisation

| Task No (continuous numbering linked to WP) | Task Name |  | Description |  |
| --- | --- | --- | --- | --- |
| T1.1 | Annual General Assembly (AGA) (held simultaneously with Executive committee, Board, and selected trainings and workshops) |  | European gathering of all members of EDF to make decisions, engage in EU and national level policy dialogue and create collective joint advocacy. In 2023, the AGA will take place in Iceland or Latvia (tbc). |  |
| T1.2 | Board meetings (accompanied by committee meetings, workshops and conferences, for organisational and economic reasons) |  | Meeting of the 31 elected members of the EDF Board, persons with diverse disabilities from across Europe. Board meetings are planned for Spring 2023 in Sweden, co-organsied our member Funktionsrätt, and for Autumn in Spain co-organised with our member CERMI (tbc). |  |
| T 1.3 | Executive committee meetings |  | Meeting of the 11 elected members of the EDF, 5 times per year. In 2023 these are planned to take place in Brussels, amongst others, and are co-organised with our members. |  |
| T 1.4 | Good governance and accountability |  | Constitutional review led by constitutional committee; EDF policies are up to date (see Annex 10 - Register of EDF organisational policies and guidance); operational plan for implementing EDF’s Green Policy |  |
| T 1.5 | Risk management |  | Risk review - twice yearly |  |
| T 1.6 | Monitoring and evaluation |  | Regular monitoring with a gender and diversity dimension, including an external evaluation, implementing external review of our IT management system, and implementation of external systems review to improve capacity of the EDF secretariat |  |
| T 1.7 | Financial management |  | Regular accounting, quarterly financial reports to the executive and biannual reports to the Board. 2022 accounts audited and submitted to the AGA; Disciplined financial follow-up according to the finance manual and procurement policy; |  |
| T 1.8 | Financial sustainability- fundraising and income diversification |  | Implementation of fundraising diversification plan; Relationship building and proposals to new sponsors, foundations, donors, and project development. |  |
| T 1.9 | Human resource management |  | Annual staff training programme including training on advocacy and/or media relations. |  |
| T 1.10 | Membership |  | Welcome and train new members and their staff (if applicable); regular coordination meetings with EU-level members |  |
| T 1.11 | EDF database and contact management |  | Training and making accessible of the new database system. |  |
| Deliverable No (continuous numbering linked to WP) | Deliverable Name | Work Package No | Lead Beneficiary | Type |
| D1.1 | Report on management of the Network | 1 | EDF | R |

Work Package 2 - Capacity building at EU and national level

| Task No (continuous numbering linked to WP) |  | Task Name |  |  | Description |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T.2.1 | Training and guidance on national transposition and implementation of EU legislation |  |  |  | Including workshops and supporting documents on topics such as the Pay Transparency Directive, the Digital Single Markets Act, the Minimum Wage Directive, the Corporate Sustainability Reporting Directive, or the Energy Performance of Buildings Directive (if adopted), or the Audiovisual Media Services Directive. |  |  |
| T 2.2 | Toolkit for members on enforcement of EU law |  |  |  | This toolkit will present different means of enforcement of EU law and how DPOs and individuals can participate, such as infringement procedures, petitions, complaints to other enforcement bodies, or strategic litigation. |  |  |
| T 2.3 | Supporting EDF members whose Member States are undergoing review by the CRPD committee |  |  |  | Online trainings, reviewing draft Alternative Reports, preparing EDF members for the sessions of the UN CRPD Committee, responding to ad-hoc questions of members on national and European CRPD review. |  |  |
| T 2.4 | Supporting EDF members undergoing review by the UN Committee on Elimination of Discrimination Against Women (CEDAW) and the Council of Europe’s Groups of Experts on Action against Violence (GREVIO) |  |  |  | Online trainings, reviewing the draft Alternative Reports, preparing EDF members for the sessions of the UN CEDAW Committee or meetings with GREVIO, and responding to ad-hoc questions of members in the context of the review. |  |  |
| T 2.5 | Training on data and statistics on disability |  |  |  | Supporting members to find reliable and comparable data on persons with disabilities and how to use it for successful advocacy, including those derived from the new disability indicators in the ESRPD for 2023 and an update on recent developments from Eurostat. |  |  |
| T 2.6 | Capacity building series for EDF members on organisational development for DPOs |  |  |  | Training programme on organisational development for DPOs: Online Fundraising, Working with foundations, Cooperation with industry and corporations, Data protection, EDF Green Policy etc. |  |  |
| T 2.7 | Introduction to new topics of relevance at EU policy level |  |  |  | Webinars and workshops on new important topics such as: the 7th Human Rights Report on Employment, Just Transition, Sustainable and connected mobility, Artificial Intelligence, e-ID Regulation, Employment Package, AccessibleEU centre, climate action, humanitarian action and disaster risk reduction, international cooperation, or work of the UN Special Rapporteur. |  |  |
| T 2.8 | Facilitate peer exchange between EDF members |  |  |  | Online and face to face sessions on topics such as Ukraine, EU Presidencies, Combating violence against women and harmful practices, communications, Accessibility Act, etc. |  |  |
| T 2.9 | Training and orientation for new members of EDF |  |  |  | Orientation training online for new and existing members of EDF, including newly elected Board and Executive members |  |  |
| T 2.10 | Training on how to lobby EU institutions on national level |  |  |  | Training session for EDF members based on the 2022 Toolkit. |  |  |
| T 2.11 | Training for EDF members on communications |  |  |  | Practical training session for EDF members on how to engage with different communication channels, accessibility and search engine optimisation (SEO), how to better coordinate and support dissemination campaigns across the EDF Comms network and on communications strategy and campaigns |  |  |
| T 2.12 | 5th European Parliament of Persons with Disabilities |  |  |  | Bringing together the disability movement on a large scale event in Brussels to learn about the European Parliament and express their demands directly to high-level policy makers. |  |  |
| Deliverable No (continuous numbering linked to WP) |  |  | Deliverable Name | Work Package No |  | Lead Beneficiary | Type |
| D1.1 |  |  | Capacity building programme and report | 2 |  | EDF | R |

Work Package 3 - UN Convention on the Rights of Persons with Disabilities (CRPD)

| Task No (continuous numbering linked to WP) |  | Task Name | Description |  |  |
| --- | --- | --- | --- | --- | --- |
| T 3.1 |  | Mainstreaming the CRPD in all EU legal and policy initiatives | Monitor legislation and polices to ensure compliance with CRPD. Give feedback via official EU channels: roadmaps, public consultations, hearings, stakeholder meetings |  |  |
| T 3.2 |  | EU review by the CRPD Committee | Hearing on the replies to the List of issues prior to reporting by the EU; Start drafting updated Alternative Report for the Concluding observations on the EU; Publish information on EU issues prior CRPD Committee sessions that include review of European countries |  |  |
| T 3.3 |  | CRPD Monitoring Framework | Participate in work and activities of the Framework |  |  |
| T 3.4 |  | Victims’ Rights (including hate crime) | Participate in Victims’ Rights Platform; implementation of Victims’ Rights Strategy and Revision of the Directive on Victims’ Rights |  |  |
| T 3.5 |  | Access to healthcare for persons with disabilities including COVID-19 | Advocate for access to healthcare for persons with disabilities in EU initiatives, including COVID-19 and work on the European Framework on Health for persons with disabilities from WHO and the DG Sante’s work on inclusive health guidelines |  |  |
| T3.6 |  | Dissemination of 7th Human Rights Report | Disseminate EDF’s 7th human rights report on employment |  |  |
| T3.7 |  | Accessible EU elections and reform of EU electoral law - ensuring the right to vote and stand for election | EDF advocacy work towards the Council to adopt a new EU Electoral Law; Bring expertise and experience of persons with disabilities to EDRS activities aimed at making 2024 European elections accessible |  |  |
| T 3.8 |  | Gender equality and women with disabilities (in collaboration with the European Women’s Lobby) | Implementation of Gender Equality Strategy; Publish a revised EDF Manifesto on women and girls with disabilities |  |  |
| T 3.9 |  | Violence against women and girls (VAWG) with disabilities (in collaboration with the European Women’s Lobby) | Advocate for the adoption of a disability inclusive EU Directive on combatting VAWG and ratification of the Istanbul Convention; Inform Council of Europe’s Group of Experts on Action against VAWG and Domestic Violence |  |  |
| T 3.10 |  | EDF Womens’ Committee | Activities and meetings of the EDF Women’s Committee including trainings, participation in mainstream events and policy activities |  |  |
| T 3.11 |  | Advocating for inclusive youth policies and initiatives | Analysing and monitoring the implementation of EU youth policies and funding programmes (including implementation of ERASMUS+, European Solidarity Corps, etc.). Build capacity of young persons with disabilities to engage in European youth movement |  |  |
| T 3.12 |  | EDF Youth Committee | Activities and meetings of the EDF Youth Committee including trainings, participation in mainstream events and policy activities, European Youth Fest 2023 |  |  |
| Deliverable No | Deliverable Name |  | Work Package No | Lead Beneficiary | Type |
| D3.1 | Report on human rights of persons with disabilities in EU policies and programmes |  | 3 | EDF | R |
| D3.2 | Report of EDF CRPD activities |  | 3 | EDF | R |
| D3.3 | Report on participation and representation of persons with disabilities |  | 3 | EDF | R |
| D3.4 | Annual EDF report on women with disabilities |  | 3 | EDF | R |
| D3.5 | Annual EDF report on youth with disabilities |  | 3 | EDF | R |

| Work Package 4 - European Strategy on the Rights of Persons with Disabilities (ESRPD) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Task No (continuous numbering linked to WP) | Task Name |  | Description |  |  |  |  |
| T4.1 |  | Contribute to the success of the ESRPD in its institutional set-up |  | Participate in the Disability and its relevant sub-groups; Engage with all relevant institutions and bodies to advocate for the implementation of the ESRPD and the nomination of disability coordinators and their inter-institutional coordination |  |  |  |
| T4.2 |  | European Disability Card and the EU Parking Card |  | Advocate for an ambitious Disability Card and analyse Commission proposal once it is published; ensure that the Parking Card scheme is improved if revised in conjunction with the Disability Card |  |  |  |
| T4.3 |  | AccessibleEU Resource Centre |  | Contribute to successful launch of the AccessibleEU Resource Centre |  |  |  |
| T4.4 |  | European Pillar of Social Rights (EPSR) |  | Advocate for implementation of the EPSR, especially principle 17, to ensure a strong disability component in the actions such as the Directive on Adequate Minimum Wages and the EU’s Social Taxonomy. |  |  |  |
| T4.5 |  | European Semester and possible follow-up initiatives |  | Influence Semester Country Reports and Country-Specific Recommendations by giving input to Commission desk officers; Analyse recommendations and support EDF members in national advocacy towards implementation. |  |  |  |
| T4.6 |  | Employment |  | Input the Employment Package to be released in 2023; Disseminate our 7th Human Rights Report on employment including launch event and/or workshop for members (see WP 2) |  |  |  |
| T4.7 |  | Social Protection |  | Input to planned Commission framework for Social Services of Excellence for persons with disabilities; Ensure disability perspective in High-Level Expert Group on Access to Adequate and Sustainable Social Protection; advocate for policies to ease the fuel price crisis and the rise in costs of living. |  |  |  |
| T4.8 |  | Independent living and Transition from institutional to community-based care |  | Input to the planned Commission guidance on independent living and inclusion in the community; work with European Expert Group on the Transition from institutional to community-based care (EEG) monitoring EU funds |  |  |  |
| T4.9 |  | Transport accessibility |  | Monitor the implementation of mainstream EU legislation as well as specific laws such as the Rail Accessibility legislation (TSI-PRM), the Alternative Fuels Infrastructure Directive (AFID) or the Trans-European Network (TEN-T) guidelines on transport infrastructure. |  |  |  |
| T4.10 |  | EU Passengers’ Rights |  | Advocacy to influence the active decision-making procedures on Passengers’ Rights following the European Commission’s agenda, including possible follow-up actions to the 2020 – 2021 evaluation of the existing Regulations. Monitor the implementation and encourage better enforcement of existing Passengers’ Rights Regulations in all transport modes. |  |  |  |
| T4.11 |  | Digital Single Market |  | Provide recommendations on actions under the Commission strategy for the Digital Single Market/EU fit for a digital age (e.g. Digital Decade Programme, Artificial Intelligence, e-ID, etc.). Analyse proposals and advocate for ensuring alignment with the CRPD and appropriate implementation of adopted EU harmonised legislation (Web Accessibility Directive, European Electronic Communications Code, Audiovisual Media Services Directive…). |  |  |  |
| T4.12 |  | Sustainable, accessible, and inclusive built environment and transport (Green Deal) |  | Influence opportunities in EU Green Deal and the field of sustainability, energy efficiency, and digitalisation such as the Just Transition, Energy Performance of Buildings Directive, New European Bauhaus, Green Public Procurement, etc. |  |  |  |
| T4.13 |  | An accessible and inclusive European Standardisation System |  | Bring the voice of the disability movement in relevant standardisation developments, such as the European Accessibility Act requested harmonised standards and advisory bodies and working groups together with ANEC; supporting ANEC in the revision of the Standardisation Regulation; participate in standardisation fora related to accessibility, such as the European Commission Multi Stakeholder Platform on ICT Standards, the key working groups inside the European Standards bodies (CEN, CENELEC, and ETSI) to promote mainstreaming. |  |  |  |
| T4.14 |  | External dimension of the European Disability Rights Strategy (and Articles 11 and 32 of the CRPD) |  | Collaborate with the EU external services and EU delegations to ensure the implementation of international cooperation aspects of the ESRPD (chapter 6) including in the fields of international development, humanitarian action, climate action, Ukraine Disaster risk reduction and use of the OECD DAC marker |  |  |  |
| Deliverable No (continuous numbering linked to WP) | Deliverable Name |  |  |  | Work Package No | Lead Beneficiary | Type |
| D4.1 | Report on implementation of the horizontal measures of the ESRPD |  |  |  | 4 | EDF | R |
| D4.2 | Report EPSR and the European Semester |  |  |  | 4 | EDF | R |
| D4.3 | Report on independent living and DI |  |  |  | 4 | EDF | R |
| D4.4 | Report on improving accessibility in the EU |  |  |  | 4 | EDF | R |
| D4.5 | Report on ESRPD and international cooperation and “EU in the world” series report 2023 |  |  |  | 4 | EDF | R |

Work Package 5 – Dissemination and Communication

| Task No (continuous numbering linked to WP) | Task Name |  |  | Description |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T5.1 | Annual communication plan |  |  | Overall 2023 internal and external communication plan |  |  |  |
| T5.2 | Managing and updating the EDF website and members area |  |  | Keep website updated; New pages on violence against women and voting rights amongst others, news, blogs, podcasts are created and uploaded . |  |  |  |
| T5.3 | Newsletters: Disability Voice, Women’s Voice, Global Action |  |  | Growing content and audiences for newsletters; Disability Voice newsletter on topics such as Older Persons with disabilities (with AGE Platform), LGBTQI persons with disabilities in (with ILGA Europe), autism (with Autism Europe), etc. |  |  |  |
| T5.4 | Social media campaigning |  |  | Expand reach. Channels include Twitter, Instagram, Facebook, LinkedIn; |  |  |  |
| T5.5 | Disability rights in the news: Press and media |  |  | Connecting with press and media, press releases, liaison with journalists, monitoring success, |  |  |  |
| T5.6 | Top campaigns |  |  | Including topics such as the EU Disability Card (including focus on invisible disabilities), Accessibility, Violence against women, health, Right to Vote |  |  |  |
| T5.7 | 2022 Annual report and EDF History Book |  |  | Accessible annual report and special publication of EDF History Book for our 25 year anniversary |  |  |  |
| T5.8 | European Human Rights report |  |  | Research and publish 8th Human rights report on Articles 12 and 14 CRPD – legal capacity & deprivation of liberty/forced treatment |  |  |  |
| T5.9 | European awards and competitions |  |  | Cooperate with the European Commission on the Access City Award, Accessible Public Sectors’ Website Award, EDF Human Rights Photo competition on women with disabilities; European Toy Manufacturers in their Toy Awards- Empowerment Category. |  |  |  |
| T5.10 | Internal communication |  |  | Weekly, members receive the internal newsletter (“Re:Member”); analysis of use and readership of newsletter; Members areas developed and updated. |  |  |  |
| Deliverable No (continuous numbering linked to WP) |  |  | Deliverable Name |  | Work Package No | Lead Beneficiary | Type |
| D5.1 |  | Report on communications impact |  |  | 5 | EDF | R |
| D5.2 |  | 8th European Annual Human Rights Report on Articles 12 and 14 CRPD – legal capacity & deprivation of liberty/forced treatment |  |  | 5 | EDF | R |
| D5.3 |  | Annual Report and EDF History Book |  |  | 5 | EDF | R |