[image: image1.jpg]Funded by
the European Union




[image: image2.png]EUROPEAN
DISABILITY

FORUM






   
DOC-EXEC-24-01-12
Risk assessment
                                                           Document for information and discussion 
Purpose of this item

To get input from the executive on the risks EDF faces and how we can mitigate them.
Questions for the Executive Committee 

Do you have questions, comments or suggestions on the risks presented, or how we propose to management them?

Introduction        
Twice per year, or more, the executive committee reviews EDFs risks. It discusses and agrees steps to mitigate risks.  In 2023 this discussion took place in detail at 2 executive committee meeting, in February, and September. Between meetings, some members of the executive assisted also in relation to risks related to the Ukraine programme. 
This document is presented in 3 sections - Section 1 is the standing assessment of EDF general risks, which are a continuation of our past assessments.  Section 2 is focused on Risks related to our work in Ukraine and how to mitigate these. Section 3 provides a summary of risks with have been reported to EDF in 2023 and the measures taken to offset these risks. 
Section 1: General risk review 

	
	Date identified
	Risk type
	Likelihood to occur
	Severity of effect
	Ownership
	Measures to take 

	1
	2019
	Security of our website against hacking
	Possible- it already happened in the past with our previous website
	Moderate
	Communications Coordinator + team
	EDF upgraded its website domain to a new system to have higher security

Our maintenance services covered:

Monitor the sites and services used by EDF for security alerts on a daily basis and quickly apply any security patches.

Regular backup of website data and files for a period of 30 days.
Updates of the tools in place (CMS, plugins...) for security purposes.

Two technical profiles capable of managing the problems linked to the administration of a website.
A tracing tool to ensure that the potential incidents and their resolution are kept.

	2
	2015
	Losing members – decreasing capacity of National Council members and lack of capacity of members 


	Unlikely in large numbers, but possible for some national councils, however, in reality our membership grows each year. 


	Severe- EDF needs to represent all DPOs in Europe and the national DPOs should also be strong progressive human rights organisations  
	Executive and Board 
	Close attention to internal communication, joint events, supporting members initiatives; membership review to identify capacity building needs, detailed attention in specific countries 

In 4-year planning offering more training support and resources to members, capacity building programme for members including on fundraising –
Specific interventions ad hoc to be raised by the Director at the executive committee

	3
	2015
	Get stuck in the EU bubble and lose touch with concerns of persons with disabilities 
	High 
	Moderate to high
	EDF executive and secretariat 
	Plan activities which engage directly with our members and participate in members events. Ensure EDF communication about the EU is easy to understand and relevant for the everyday lives of persons with disabilities. Recent staff training/exchange on country/member visits

	4
	2022
	National members not aligned to CRPD (eg question of EDF members supporting institutions, members promoting models of segregated education or sheltered workshops, members with positions that are go against the principle of gender equality, members not being diverse and inclusive)
	Likely due to diversity in the movement and lack of resources for DPOs to build their capacity 
	Moderate
	Executive 
	Identification of actions and positions in our membership that go against the CRPD;

Active involvement of the EDF President and executive in resolving CRPD and principle related issues; 

Bilateral meetings with the members concerned to discuss views and explain the reasoning and value behind the CRPD articles; 

More regular training and workshops for the Secretariat and members to clarify the EDF and CRPD position. 

Increased opportunities for exchange , learning and growth within membership 

	5
	2015
	Too many activities- risk to lose quality - ‘mission creep’
	Likely 
	Moderate 
	Executive Director and Deputy Director and Executive 
	Careful work planning, regular staff meetings, activity planning with executive

We must also be disciplined about what travel we do, which events we attend and projects we engage with. 
New EDF strategy to recheck our priorities and direction

	6
	2015
	EDF financial situation/ funding decreases 
	Moderate ; however, our income has been growing annually and our sources of funding diversifying.
	High 
	Executive Director  
	Careful management of finances and reporting

Investment in fundraising, sponsorship

Increased focus on resource mobilization and support to members in this field in next 4-year plan. 

Funding and grants officer hired and in post since end of 2021; she focuses on resource mobilization for EDF and members 

	7
	2021
	Financial- loss of EU funding 
	moderate
	High
	Executive Director
	Excellent preparation of 4-year workplan, strong monitoring and financial follow-up. Strengthening the financial team and systems (Finance manual update at the finance committee meeting in November). Financial sustainability work. 

	8
	2022
	Financial – effects of increased inflation and cost of living/operating the organization
	High
	Moderate
	Director

Executive
	Ensure that we can compensate for indexation of salaries under the Operating Grant; lobby the Commission to ease the rules or increase funding according to indexation

	9
	2020
	COVID 19 pandemic and consequences 
	Possible re-emergence of pandemic and related restrictions 
	This depends on how the pandemic reemerges as a public health concern affecting the general population, and then also our work, travel etc. 
	Executive 
	Continuous monitoring of threat level at the European level, and national level in any country we plan to have an event. 

	
	2022
	IT and e-mail systems – prone to hacking and spoofing addresses
	High (already happened)
	High – it might lead to untrustworthiness and reputational damage
	Secondary – Communications Coordinator
	Hiring of an external expert to audit and improve the e-mail systems

Regular contacts and complaints to our IT service provider.

Possible implementation of new, more secure systems. 

Training to staff on cyber awareness and security.

	
	2023
	Public accusations towards the International Disability Alliance have a negative impact on the reputation EDF
	High
	High 
	EDF executive
	


Section 2: Risks related to the war in Ukraine and EDF work

	
	Date identified
	Risk type
	Likelihood to occur
	Severity of effect
	Ownership
	Measures to take 

	1
	December 2022
	Prolonged war with less attention and funding over time, reducing EDFs ability to continue is work and support to members 
	Likely
	Moderate on EDF

Severe on DPOs and persons with disabilities in Ukraine 
	External
Within EDF: Programme Coordinator
	Advocacy to the EU and other donors to ensure continued engagement towards people with disabilities in Ukraine, funding mobilization to maintain support, focus on EU accession to ensure long term perspective in support to the disability movement in Ukraine. EDF has now planned to phase out of support to DPOs at the end of 2024 - in 2024 country activities will take place in Ukraine, Moldova, Poland and European Activities run by EDF and Sustento.

	3
	February 2022 onwards
	Safety and security - to monitor the programme in Ukraine and participate in activities travel there would be ideal. Our current travel insurance does not cover it.
	Possible
	Extreme: staff or consultants injury or loss of life

Moderate: mental health impact of staff traveling

Costs of travelling + extra insurances etc
	EDF Executive Director
	Travel to Ukraine is only permitted if considered essential to our programme - and no staff will be obliged to travel to Ukraine. 

EDF staff and consultants have both travelled to Ukraine in 2023 for programme visits, training, and program evaluation without incident. (Although Kiev was attacked by Russia during two visits)
Security training for staff of partners/ and EDF staff was done in October 2022. HEAT training (Hostile Environment Awareness Training)  was done for EDF staff in November 2023. Further safety and security training and HEAT (for the Ukraine program partners is planned to continue in 2024 as part of programme activities.
Security policy was updated for Ukraine 

Insurance is challenging. EDF has purchased travel insurance for travelling to Ukraine, including local Ukrainian insurance - but our full workplace insurance does not cover Ukraine, and this remains something we need to find more comprehensive solutions for. We currently contract specific insurance for each Ukraine trip and have a travel application for internal use to ensure all risks have been considered and mitigated. 

	4
	February 2022 onwards
	Child Protection and safeguarding /EDF is directly funding our members and partners who are providing direct support to adults and children in high risk situations, displaced, migrated and in institutions 
	Possible  
	Extreme to EDF if we fund activities that result in abuse 
	EDF Executive Director 
	Safeguarding policy included in partner contracts, Safeguarding training was given to partners in July 2022, and support is continually offered.

New safeguarding trainings will be provided through German Foreign Ministry funding in 2024. 

	5
	April 2022
	Financial risks – difficulty for our members in implementation of projects, lack of financial capacity for reporting, mismanagement of funding, delays in implementation or reporting– this will all impact EDF relationship with donors 

Corruption levels are high in Ukraine 
	Possible 
	Moderate.
	EDF Finance manager and Ukraine team (especially Admin and Finance reporting Officer)
	Use of EDF financial manual including new elements on partnership development

Hiring finance/ administration expert for project, increasing time of accountant, support to members by EDF staff (each country knows who their focal point is), training and project visits (ongoing).

Financial and reporting training for the program members

Training of EDF staff on finance manual and fraud policy was done in 2023; 

	6
	April 2022
	Mental health impact of the project of EDF staff 
	Possible. 
	Moderate 
	EDF Executive Director 
	Regular meetings with Ukraine team, Tuesdays, to monitor workload and prioritise

Ensuring adequate staffing and supervision of staff (according to EDF HR manual)
Training on Stress Management and Well-Being was given to partners and EDF staff in October 2022.

Further psychosocial support can be offered (at least one partner – NAPD – is already running PSS retreats for members.

	
	Aug 2023
	Staff recruitment challenges and attrition - There is a growing shortage of people in the Ukraine workforce who have experience in humanitarian action and/or disability inclusion. This is being increased because of the severity and longevity of the situation (there are many job opportunities with UN agencies and large humanitarian organisations, and many qualified people are leaving the country).
	Likely
	Moderate
	EDF and partner human resource departments and staff managers
	Practice good management; check staff morale; provide support where needed; offer training and longer term opportunities where possible

	9
	July 2022
	Closing of the Ukraine programme at the end of the funding cycle in December 2024
	Probably 
	Moderate on EDF as an organisation, but significant for staff concerned.

High for DPOs in Ukraine /Moldova and Poland
	EDF Executive Director
	Transparency with partners, members and staff about the timeframes for funding; this was announced already at the October 2022 partners meeting and all progress and plans discussed regularly with partners
Collaboration with funders to look for future options

Training for EDF members and partners in grant-writing; introducing members and partners to potential funders 

Phase out of unfunded parts of the programme 

Manage staff who will leave and redeploy staff to other projects as possible and suitable

	10
	November/December 2023
	Political risk – growing media attention to our demands on accessible infrastructure and implied criticism of the Ukraine government may lead to ill will by the political establishment
	Possible
	Moderate to low
	EDF international Cooperation manager with support of Communications Coordinator
	Ensuring key points are aligned and credible

Regular communications catch-up between press liaison and team

Contact with Ukrainian members

	11
	August 2023
	Financial – Overspending due to the increasing of inflation and salaries indexation as well as due to the occurrence of unforeseen situations that require additional expenses (additional trips, trainings), considering the fact that we are addressing an emergency situation
	Possible
	Moderate
	EDF Finance manager and Ukraine team (especially Admin and Finance reporting Officer)
	Ensuring adequate financial management, Continuous monitoring of the expenses at the EDF level and partners reports

	12 
	
	Changing of the target group’s needs - The dynamic nature of emergency situations may lead to rapidly evolving needs among affected target groups and OPD’s. Failure to adapt quickly to changing circumstances may result in an inadequate response that does not address the most critical needs
	Possible
	Moderate
	EDF: Programme Coordinator
	Regular meetings with Ukraine team, Tuesdays, to monitor the needs.

Program partners are submitting monthly summary reports and quarterly detailed narrative reports
EDF contracted in October 2023 a consultant to undertake a series of external evaluations of its work responding to the war in Ukraine. The purpose of these evaluations is to help EDF and its partners learn from the programme so far, identifying strengths and weaknesses, to make informed decisions moving forward and be able to provide the most effective possible response to similar future situations. First evaluation report will be available on January 2024

	13
	December 2023
	Issues with health and well-being of project leadership in Ukraine and staff turnover can hamper project implementation
	Likely
	High
	EDF management team, Empower Ukraine project staff
	Hiring a sufficient number of highly qualified and experienced experts by partner organisations in Ukraine in the project-related areas.  

Ensuring interchange of staff in Ukraine and delegating authority by project leaders to employees to allow them to make project-related decisions.  

Additionally, the project will make use of engaging experts / consultants and consultancy companies to minimise the risk of fall-out (e.g. in the areas of MHPSS, security and safety, communication and safeguarding).  

	14
	December 2023
	EDF inability to make timely money transfers to our partner organisations in Ukraine because of EDF cash flow needs
	Likely
	High
	EDF finance team, EDF management, Empower Ukraine project staff 
	Constant communication between EDF operational team, Empower Ukraine project staff and partners in Ukraine.  Robusting financial management systems, establishing clear financial procedures to ensure transparency, accountability, and compliance with contractual obligations.

	15
	December 2023
	Significant escalation of the active fighting beyond the current areas of hostilities.  

Blackouts due to Russian missile attacks. 

This may impede project implementation and impact the ability to monitor activities through field visits and other means.
	Likely
	Medium
	EDF management, Empower Ukraine project staff
	Risk assessment and mitigation will be addressed through the regular security analysis and consultations with Ukrainian partners and security service providers (e.g. SOS International). 

Acquiring power generators capable of providing local organisations with electricity.

	
	
	
	
	
	
	


Section 3- Incidents/risks reported 2023
1. Accusation (found on social media- Facebook) towards an NGO, member of one of our partners, related to alleged misuse of funds and humanitarian materials. (23rd August 2023)

Response- Catherine + Ukraine team, informed EDF President

This information was shared with the EDF director by a staff member. It included facebook comments towards the local organisation, with claims that all humanitarian goods (not EDF support specifically) did not reach everyone who needed them. The EDF Director took the following steps: 

· Study of the comments, using google translate

· Contact with the umbrella organisations, asking and receiving detailed explanations

· Clarifying that it is important to respond clearly to these comments

· External evaluators who will study our programme in Ukraine in 2023 will visit the partner and also explore the complaint mechanisms they have and see is extra training is needed (there has already been training)

· Ongoing monitoring and training of our partners

In conclusion, there was no evidence of any misuse of funds or materials, but the need for good communication and responses to feedback will be built into the programme. 
2. Report via email to EDF, that EDF reports include references to small group homes which are not aligned to the CRPD. (September 21, 2023)

Response: Catherine and Ukraine team. Involved from the Executive: Nadia Hadad and Maureen Piggot. EDF president informed. 

a. EDF executive member approached EDF in relation to 2 reports supported or drafted by EDF

b. Report one was from a partner, and the partner made changes in the document to remove references to small group homes- the conversation was very helpful to clarify EDFs position on independent living to the EDF partner

c. Report 2 was from a workshop led by EDF and partners on DI. There was a detailed explanation given via email on the context of the language. 

This is an issue which is being constantly monitored and training provided continuously to partners to ensure there is a good understanding of choice, autonomy and independence for persons with disabilities and a move from institutional to community based support. EDF must find a strong mechanism for coordination on deinstitutionalisation in Ukraine. Right now there is a coordination/working group on DI for children, but for adults the programmes and advocacy are quite uncoordinated. Since the issue of institutional segregation is so profound in Ukraine- both for children and adults this situation requires careful and continuously monitoring and capacity building. In addition, the reputation of EDF as a supporter was reviewed to ensure our partners can independently issue reports without EDF being held responsible for editorial decisions. 

3. Safeguarding issue in Mahala institution- September 2023

Response: EDF executive Director + Ukraine team

Involved from Executive: Maureen Piggot

EDF is supporting the Ukrainian Child Rights Network (UCRN) in a model DI programme at this institution. There were reports in the press about neglect of children in the institution. There are 37 institutions like this in Ukraine (children with disabilities) with very high level of neglect. On top of this, about 42 of the 54 children there are also displaced, having originally come from Eastern Ukraine. EDF convened a meeting of staff and our Safeguarding focal point Maureen Piggot to assess the situation and ensure that we take all measures to ensure children in the programme are protected. EDF staff and consultants met with UCRN and the director of the institution, and the local authorities to talk through all the issues. The child concerned, who died earlier this year, in hospital with an epilepsy related condition, was not part of the EDF programme. However, there are many children at risk of malnutrition and neglect in Ukraine’s 37 institutions for children with disabilities. In a mission to Ukraine in November the EDF Director met partners in Mahala and Kyiv, and met with UNICEF Ukraine, and save the children and discussed the need for individualized support, and family based care for all the children currently living in institutions in situations of neglect. UCRN currently have a team working in Mahala providing daily support to the children as part of the plan to transition to family based care.  The EDF president also received the Safeguarding report in September.  We continue to monitor the situation closely. 

[image: image3.jpg]Avenue des Arts 7-8 Tel+3223290059 info@edf-feph.org
B1210 Brussels - Belgium Fax+322329 0059 www.edf-feph.org



1

