## EDF WORKPLAN 2025

### 4.1 Work Plan

| Work Plan Provide a brief description of the overall structure of the work plan (list of work packages or graphical presentation (Pert chart or similar)). |  |
| --- | --- |
| EDF’s annual Work Plan for 2025 is divided into 7 Work Packages in total. The first 5 Work Packages are covered by the European Commission’s operating grant under the Citizens, Rights, and Values Programme. Work Package 6 summarizes our work on International Cooperation and Humanitarian Action financed by other sources, and Work Package 7 is a list of projects that feed into the different work areas. The overall focus is on implementation of the UN Convention on the Rights of Persons with Disabilities (CRPD), the implementation of the European Strategy on the Rights of Persons with Disabilities (ESRPD) and capacity building and training of EDF’s membership on national and EU level. Management of the network and communication and dissemination of EDF’s work is of course also included. All activities include persons with disabilities in their full diversity. WP 1 – General Management and running of the organisation WP 2 – Capacity building at EU and national level WP 3 – UN Convention on the Rights of Persons with Disabilities (CRPD) WP 4 – European Strategy on the Rights of Persons with Disabilities (ESRPD) WP 5 – Dissemination and communication WP 6 – International Cooperation and Humanitarian Action WP 7 – List of projects |

### 4.2 Work packages, activities, resources and timing

#### Work Package 1

| Work Package 1: General management and running of the organisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  |  | M1 – M12 | Lead Beneficiary: |  |  |  | EDF |  |  |  |  |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The Disability Movement in Europe is supported by an effective, diverse, financially stable secretariat - The organisation practices good governance in line with the Belgian law and practices the highest levels of transparency, accountability, sustainability and membership engagement - The EDF governing body meetings are organised and run smoothly in collaboration with EDF members. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task No (continuous numbering linked to WP) | Task Name |  |  |  |  | Description |  |  |  | Participants |  |  |  |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  |  |  |  |  | Name |  | Role (COO, BEN, AE, AP, OTHER) |  |  |  |
| T1.1 | Annual General Assembly (AGA) (held simultaneously with Executive committee, Board, and selected trainings and workshops) |  |  |  |  | European gathering of all members of EDF to make decisions, engage in EU and national level policy dialogue and create collective joint advocacy. In 2025, the AGA will take place in Croatia (tbc). |  |  |  | EDF |  | COO |  |  | No |
| T1.2 | Board meetings (accompanied by committee meetings, workshops and conferences, for organisational and economic reasons) |  |  |  |  | Meeting of the 31 elected members of the EDF Board, persons with diverse disabilities from across Europe. Board meetings are planned for Spring 2025 in Poland, and for Autumn in Denmark (tbc). |  |  |  | EDF |  | COO |  |  | No |
| T 1.3 | Executive committee meetings |  |  |  |  | Meeting of the 11 elected members of the Executive committee of EDF, 5 times per year. In 2025 these are planned to take place in Brussels, amongst others, and are co-organised with our members. |  |  |  | EDF |  | COO |  |  | No |
| T 1.4 | Good governance and accountability |  |  |  |  | EDF policies are up to date (see Annex 10 – Register of EDF organisational policies and guidance) and EDF implements the new organisational strategy. This includes clarifying and consolidating inter-team relationships, roles and responsibilities within the Secretariat and establishing regular moments for review, reflection and learning within the Secretariat. Our data protection policy will be reviewed (together with privacy and cookies statements) and updated as needed. |  |  |  | EDF |  | COO |  |  | No |
| T 1.5 | Risk management |  |  |  |  | Risk review – twice yearly |  |  |  | EDF |  | COO |  |  | No |
| T 1.6 | Monitoring and evaluation |  |  |  |  | Regular monitoring with a gender and diversity dimension across all EDF’s work; continue with the implementation of the recommendations of the 2023 external evaluation; |  |  |  | EDF |  | COO |  |  | No |
| T 1.7 | Financial management |  |  |  |  | Regular accounting, quarterly financial reports to the executive and biannual reports to the Board. 2024 accounts audited and submitted to the AGA; Disciplined financial follow-up according to the finance manual and procurement policy. |  |  |  | EDF |  | COO |  |  | No |
| T 1.8 | Financial sustainability- fundraising and income diversification |  |  |  |  | Continuing the implementation of fundraising diversification plan; Relationship building and proposals to new sponsors, foundations, donors, and project development. |  |  |  | EDF |  | COO |  |  | No |
| T 1.9 | Human resource management |  |  |  |  | Annual staff training programme including training on how to make EDF’s work more inclusive to persons with intellectual disabilities, navigating the intersection of health and disability, older persons, youth, advocacy for example on the CRPD Committee and the EU review, communication trends, cyber security, working on the new “cloud” IT environment, accessibility, etc. |  |  |  | EDF |  | COO |  |  | No |
| T 1.10 | Membership |  |  |  |  | Welcome and train new members and their staff (if applicable); regular coordination meetings with EU-level members; keep database with members’ contacts updated |  |  |  | EDF |  | COO |  |  | No |
| T 1.11 | IT infrastructure and security |  |  |  |  | Migrate EDF’s server structure to the Cloud for better sharing of information and IT security. |  |  |  | EDF |  | COO |  |  | No |
| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone No (continuous numbering not linked to WP) |  | Milestone Name |  |  | Work Package No |  | Lead Beneficiary |  | Description | Due Date (month number) |  |  | Means of Verification |  |  |
| Deliverable No (continuous numbering linked to WP) |  | Deliverable Name |  |  | Work Package No |  | Lead Beneficiary |  | Type | Dissemination Level | Due Date (month number) |  |  | Description (including format and language) |  |
| D1.1 |  | Report on management of the organisation |  |  | 1 |  | EDF |  | R | SEN | 12 |  |  | Word document in English |  |

#### Work Package 2

| Work Package 2: Capacity building at EU and national level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  |  |  | M1 – M12 |  |  | Lead Beneficiary: |  |  | EDF |  |  |  |  |  |  |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - A comprehensive training and development programme for EDF members, partners, and other stakeholders at national, international, and EU level is implemented. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task No (continuous numbering linked to WP) |  | Task Name |  |  | Description |  |  |  |  |  |  |  | Participants |  |  |  |  | In-kind Contributions and Subcontracting (Yes/No and which) |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Name | Role (COO, BEN, AE, AP, OTHER) |  |  |  |  |  |
| T 2.1 | Training and guidance on national transposition and implementation of EU legislation that concern persons with disabilities |  |  |  |  | Including webinars, workshops and supporting documents on policies such as the European Accessibility Act, , the Victims’ Rights Directive, the Standards for Equality bodies, or the Energy Performance of Buildings Directive.directives, |  |  |  |  |  |  | EDF | COO |  |  | No |  |  |
| T 2.2 | Training and guidance on new and on-going policy initiatives and developments that concern persons with disabilities |  |  |  |  | Including webinars, workshops, and supporting documents on the composition and political priorities of the new European Commission and European Parliament after the elections and policies such as the updated European Disability Strategy 2021-2030, covering actions from 2025-2030, and how to use the CRPD Committee’s concluding observations on the EU for advocacy. |  |  |  |  |  |  | EDF | COO |  |  | No |  |  |
| T 2.3 | Supporting EDF members whose Member States are undergoing review by the CRPD committee |  |  |  |  | Reviewing draft Alternative Reports, preparing EDF members for the sessions of the UN CRPD Committee through online or in person trainings, responding to ad-hoc questions of members on national and European CRPD review. |  |  |  |  |  |  | EDF | COO |  |  | No |  |  |
| T 2.4 | Supporting EDF members undergoing review by the UN Committee on Elimination of Discrimination Against Women (CEDAW) and the Council of Europe’s Groups of Experts on Action against Violence (GREVIO) |  |  |  |  | Reviewing the draft Alternative Reports, preparing EDF members for the sessions of the UN CEDAW Committee or meetings with GREVIO, and responding to ad-hoc questions of members in the context of the review. |  |  |  |  |  |  | EDF | COO |  |  | No |  |  |
| T 2.5 | Capacity building series for EDF members on organisational development for Organisations of Persons with Disabilities (OPDs) |  |  |  |  | Trainings to increase organizational capacity of members and peer exchange of funding sources and functioning of national OPDs. Based on Members’ need survey conducted in 2023, we decided that in 2025 we will organise fundraising training and public speaking or leadership and activism training. |  |  |  |  |  |  | EDF | COO |  |  | No |  |  |
| T 2.6 | Facilitate peer exchange between EDF members |  |  |  |  | Online and face to face sessions on topics such as EU Presidencies, the Accessibility Act and its standardisation developments, access to healthcare, enforcement of EU law, the transposition of the directive on combating violence against women, ending forced sterilisation, legal capacity and supported decision-making, successful advocacy and awareness-raising campaigns led by our members, monitoring of EU legislation on national level (e.g. Use of Structural Funds) etc. |  |  |  |  |  |  | EDF | COO |  |  | No |  |  |
| T 2.7 | Training and orientation for new members of EDF |  |  |  |  | Orientation training online for new and existing members to get to know EDF as an organisation |  |  |  |  |  |  | EDF | COO |  |  | No |  |  |
| T 2.8 | Toolkit and webinar on the European Disability Card and Parking Card |  |  |  |  | This document will contain information about the content of the Directive adopted in 2024. It will also give practical advice and guidance to EDF members to advocate for an ambitious transposition into national law. |  |  |  |  |  |  | EDF | COO |  |  | No |  |  |
| T 2.9 | Training for EDF members on communications |  |  |  |  | Practical training session for EDF members on accessibility of communications, campaigning and communications trends and tools. |  |  |  |  |  |  | EDF | COO |  |  | No |  |  |
| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone No (continuous numbering not linked to WP) |  |  | Milestone Name |  |  |  |  | Work Package No | Lead Beneficiary |  | Description | Due Date (month number) |  |  | Means of Verification |  |  |  |  |
| Deliverable No (continuous numbering linked to WP) |  |  | Deliverable Name |  |  |  |  | Work Package No | Lead Beneficiary |  | Type |  | Dissemination Level | Due Date (month number) |  | Description (including format and language) |  |  |
| D2.1 |  |  | Capacity building programme |  |  |  |  | 2 | EDF |  | R |  | PU | 12 |  | Word document in English |  |  |

#### Work Package 3

| Work Package 3: UN Convention on the Rights of Persons with Disabilities (CRPD) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  | M1 – M12 | Lead Beneficiary: |  | EDF |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |
| - New and revised legislation and EU processes including newly emerging issues are aligned to promote the CRPD - EDF and its members contributes to a thorough review of the EU’s implementation of the CRPD by the UN CRPD committee - Persons with disabilities are included in new and revised EU human rights policies and initiatives and new priority areas are identified - Persons with disabilities and their representative organisations in all their diversity are meaningfully involved in all EU policy matters and democratic decision-making processes - Specific improvements are made in the situation of women and girls with disabilities at the EU and national level - Specific improvements are made in the situation of young persons with disabilities participate in youth and disability policy |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |
| Task No (continuous numbering linked to WP) | Task Name |  |  | Description |  | Participants |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  | Name | Role (COO, BEN, AE, AP, OTHER) |  |
| T 3.1 | Mainstreaming the CRPD in all EU legal and policy initiatives, as well as in institutional structures of the new Commission and European Parliament. |  |  | Monitor legislation and polices to ensure compliance with CRPD and increase the diversity of voices representing EDF in EU policy influencing activities. Give feedback via official EU channels: roadmaps, public consultations, hearings, stakeholder meetings. Meetings with new EU leaders and institutional structures in support of the CRPD implementation in the European Commission and European Parliament, including the Disability Intergroup. |  | EDF | COO | No |
| T 3.2 | Ensuring participation of persons with disabilities in EU Council Presidencies |  |  | Develop new EDF approach for strengthening engagement with the Council of the EU. Implementation of the “Presidency Scorecard” system that was developed in 2024 to assess the inclusiveness of the Polish and Danish EU Presidencies. |  | EDF | COO | No |
| T 3.3 | Ensuring a CRPD perspective in the next Multiannual Financial Framework (MFF) of the EU |  |  | Advocate for a disability inclusive MFF in the relevant policy areas, including the Citizens, Equality, Rights, and Values Programme (CERV) in collaboration with Civil Society Europe, EU structural and investment funds in relation to independent living, accessibility, social inclusion in collaboration with Social Platform, and other relevant funding programmes. |  | EDF | COO | No |
| T 3.4 | EU review by the UN Committee on the Rights of Persons with Disabilities (CRPD) and CRPD Monitoring Framework |  |  | Ensure that the perspective of Organisations of Persons with Disabilities is included in the review of the EU by the CRPD (publish and promote alternative Reports, support EDF members submitting reports, and participate in the review session in Geneva). Publish an analysis of the Concluding observations on the EU by the CRPD Committee. Participate in work and activities of the EU CRPD Monitoring Framework. Draft and submit information notes on European issues for the session of the CRPD Committee . Draft and publish a report on CRPD independent monitoring frameworks in Europe. |  | EDF | COO | No |
| T 3.5 | Disability rights in Equality and Non-discrimination legislation |  |  | Advocate for adoption and/or implementation of the proposed Horizontal Equal Treatment Directive and new equality strategies post-2025 in collaboration with other non-discrimination NGOs such as AGE Platform Europe, ILGA Europe, ENAR, Equinet, ERGO Network, etc. Advocate for EU and national actions to combat hate speech and hate crime against persons with disabilities. |  | EDF | COO | No |
| T 3.6 | Legal capacity and initiatives on the protection of adults |  |  | Advocacy on EU’s promotion of supported-decision making and for compliance with the CRPD of the proposal for a Regulation on the protection of adults and ratification of the 2000 Hague Convention. |  | EDF | COO | No |
| T 3.7 | Victims’ Rights (including hate crime) |  |  | Participate in Victims’ Rights Platform; implementation of Victims’ Rights Strategy and Revision and implementation of the Directive on Victims’ Rights; Advocacy for a victims’ rights strategy post 2025, inclusive of victims with disabilities. |  | EDF | COO | No |
| T3.8 | Access to healthcare for persons with disabilities |  |  | Advocate for access to healthcare for persons with disabilities in EU initiatives, including DG SANTE work on inclusive health guidelines, the comprehensive approach to mental health, Europe’s Beating Cancer Plan, and the work of the European Parliament in this policy domain. Continue the work on the European Framework on Health for persons with disabilities (WHO) as well as advocacy on mental health at the Council of Europe (campaign on the draft additional protocol to the Oviedo Convention and recommendations on voluntary measures). |  | EDF | COO | No |
| T 3.9 | Drafting of 10th Human Rights Report on Assistive Technologies |  |  | Research background and draft text of the 10th Human Rights Report on Assistive Technologies |  | EDF | COO | No |
| T 3.10 | Gender equality and women with disabilities (in collaboration with the European Women’s Lobby) |  |  | Analyse and monitor the implementation and evaluation of the EU’s Gender Equality Strategy and the Gender Action Plan III, and advocate for strategy post 2025. Advocate for the ambitious transposition of a disability inclusive EU Directive on combatting violence against women and girls with disabilities, and implementation of the Istanbul Convention by the EU, and ratification by Member States who have not yet ratified it. Campaign to prevent and end forced sterilisation against women and girls with disabilities in the EU and at national level. |  | EDF | COO | No |
| T 3.11 | EDF Women’ Committee |  |  | Activities and meetings of the EDF Women’s Committee, including one meeting in Greece (tbc). Work will include the promotion of the third EDF manifesto on women and girls with disabilities to the new policy-makers in the Commission and Parliament, and participation in mainstream events and policy activities. Participation in the work and activities of the European Womens’ Lobby, including its Board to which EDF was elected in June 2023, the feminist economic working group and the observatory on violence against women |  | EDF | COO | No |
| T 3.12 | Advocating for inclusive youth policies and initiatives |  |  | Analysing and monitoring the implementation of EU youth policies, such as ERASMUS+ as part of the informal ERASMUS+ coalition, European Solidarity Corps, the revision of the Youth Guarantee, the Directive on Traineeships, etc. |  | EDF | COO | No |
| T 3.13 | EDF Youth Committee |  |  | Organise activities and meetings of the EDF Youth Committee including, participation in mainstream youth policy activities and events, such as the European Youth Event in June 2025. Strengthen the engagement of youth in EDF’s work and building capacity of young persons with disabilities to engage in European youth movement. Explore EDF associate membership in the Youth Forum. |  | EDF | COO | No |

| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) |  | Means of Verification |  |  |
| Deliverable No (continuous numbering linked to WP) | Deliverable Name | Work Package No | Lead Beneficiary | Type |  | Dissemination Level |  | Due Date (month number) | Description (including format and language) |  |
| D3.1 | Report on participation and representation of persons with disabilities in EU policy | 3 | EDF | R |  | PU |  | 12 | Word document in English |  |
| D3.2 | Report on EDF CRPD activities | 3 | EDF | R |  | PU |  | 12 | Word document in English |  |
| D3.3 | Report on human rights of persons with disabilities in EU policies and programmes | 3 | EDF | R |  | PU |  | 12 | Word document in English |  |
| D3.4 | Annual EDF report on women with disabilities | 3 | EDF | R |  | PU |  | 12 | Word document in English |  |
| D3.5 | Annual EDF report on youth with disabilities | 3 | EDF | R |  | PU |  | 12 | Word document in English |  |

#### Work Package 4

| Work Package 4: European Strategy on the Rights of Persons with Disabilities (ESRPD) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: | M1 – M12 |  | Lead Beneficiary: | EDF |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |
| - The ESRPD is implemented and monitored at EU and national level with direct involvement of Organisations of Persons with Disabilities (OPDs), including through the Disability Platform. - The ESRPD is amended with new flagship initiatives and actions proposed by OPDs for 2025-2030. - The European Pillar of Social Rights and the European Semester Process contribute to a stronger social Europe - Advance the transition from institutional to community-based care including support to independent living. - All modes of transport, the built environment, Information and Communication Technologies and all other products and services become more accessible for persons with disabilities. - EU actions towards sustainability and climate action take persons with disabilities into consideration. - Persons with disabilities and OPDs are included in the EU’s global work on international cooperation, and humanitarian action. |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |
| Task No (continuous numbering linked to WP) |  | Task Name | Description |  | Participants |  | In-kind Contributions and Subcontracting (Yes/No and which) |  |  |
|  |  |  |  |  | Name | Role (COO, BEN, AE, AP, OTHER) |  |  |
| T4.1 |  | Contribute to the success of the ESRPD in its institutional set-up | Advocate for a second set of actions for the Disability Strategy 2025 – 2030; Participate in the Disability Platform and its events and relevant sub-groups; Engage with all relevant institutions and bodies to advocate for the implementation of the ESRPD and the nomination of disability coordinators and their inter-institutional coordination; Participate in relevant actions of the AccessibleEU centre. |  | EDF | COO | No |  |  |
| T4.2 |  | European Disability Card and the EU Parking Card | Advocate for inclusion and accessibility in the related delegated/implementing acts; continue advocacy for further legislation on freedom of movement. See also Activity T 2.8. |  | EDF | COO | No |  |  |
| T4.3 |  | European Pillar of Social Rights (EPSR) | Advocate for implementation of the EPSR, especially principle 17, to ensure a strong disability component (if still applicable); Disseminate the most recent data on the social inclusion pf persons with disabilities (particularly in employment) using Eurostat’s Disability Database, explore the potential role of public procurement policies in furthering the inclusion of persons with disabilities; Participate in the Social Pillar Task Force within Social Platform and provide input to joint advocacy with other Social Platform members |  | EDF | COO | No |  |  |
| T 4.4 |  | European Semester and possible follow-up initiatives | Influence Semester Country Reports and Country-Specific Recommendations by giving input to Commission desk officers; Analyse recommendations and support EDF members in national advocacy towards implementation. |  | EDF | COO | No |  |  |
| T4.5 |  | Employment | Recommendations to Member States and the Commission on targets for increasing the employment rate of persons with disabilities and reducing employment rate gaps, including entrepreneurship and the use of state aid; Provide policy proposals to the European Commission to enhance the meaningful employment of persons with disabilities in the EU in the open labour market through actions that will be integrated into the EU Strategy on the Rights of Persons with Disabilities; |  | EDF | COO | No |  |  |
| T4.6 |  | Social Protection | Advocate for EU policies to ease the rise in costs of living. Investigate possibility to include portability of disability-related services in Social Security Coordination rules; Advocate for the use of personal budgets when providing funding for services for persons with disabilities. |  | EDF | COO | No |  |  |
| T4.7 |  | Independent living and transition from institutional to community-based care | Advocate for strong clauses in the Regulations for Cohesion funding that will accelerate the transition from institutional to community-based care and independent living; work with European Expert Group on the Transition from institutional to community-based care (EEG). |  | EDF | COO | No |  |  |
| T4.8 |  | Transport accessibility | Monitor the implementation of mainstream EU transport legislation such as the Trans-European Network Regulation (TEN-T) or the Alternative Fuels Infrastructure Regulation (Electric Vehicle Recharging Stations). Advocate for improvements in transport accessibility in all modes and in particular advocate for an ambitious revision of the Rail Accessibility Regulation (TSI-PRM). |  | EDF | COO | No |  |  |
| T4.9 |  | EU Passengers’ Rights | Advocacy to influence the decision-making procedures on Passengers’ Rights following the European Commission 2023 proposals on enforcement and multimodal transport, with a focus on improving air passenger rights. Monitor the implementation and encourage better enforcement of existing Passengers’ Rights Regulations in all transport modes in collaboration with AGE Platform Europe and other transport stakeholders. |  | EDF | COO | No |  |  |
| T4.10 |  | Digital Single Market | Provide policy recommendations on EU policies in the digital domain, such as the Digital Euro Regulation, and accessibility requirements in these policies. Monitor developments and advocate for the implementation of specific accessibility legislation such as the European Accessibility Act, Web Accessibility Directive, European Electronic Communications Code, and Audiovisual Media Services Directive. |  | EDF | COO | No |  |  |
| T4.11 |  | A disability-inclusive Green Deal and Just Transition | Influence opportunities in the follow-up to the EU Green Deal and the field of sustainability, amongst others through our work in the Just Transition Alliance. Encourage research on effect of Just Transition on persons with disabilities. Represent persons with disabilities in relevant discussions both in their role as consumers and users as well as employees in policy fields related to transport, the built environment, energy, etc. |  | EDF | COO | No |  |  |
| T4.12 |  | An accessible and inclusive European Standardisation System | Bring the voice of the disability movement in relevant standardisation developments, such as the European Accessibility Act requested harmonised standards and advisory bodies and working groups together with ANEC (Representative organisation of consumers in standardisation); participate in standardisation fora relevant to accessibility, such as the European Commission Multi-Stakeholder Platform on Information and Communication Technology (ICT) Standards, the key working groups inside the European Standards bodies (CEN, CENELEC, and ETSI) to promote mainstreaming of accessibility and inclusion of persons with disabilities. Advocate for a more inclusive European Standardisation System (Regulation 1025/2012). |  | EDF | COO | No |  |  |
| T4.13 |  | Global dimension of the European Disability Rights Strategy (and Articles 11 and 32 of the CRPD) | Collaborate with the EU external services and EU delegations to ensure the implementation of international cooperation aspects of the ESRPD (chapter 6) including in the fields of international development and humanitarian action. |  | EDF | COO | No |  |  |

| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification |  |  |  |  |  |
| Deliverable No (continuous numbering linked to WP) | Deliverable Name | Work Package No | Lead Beneficiary | Type |  |  | Dissemination Level | Due Date (month number) |  | Description (including format and language) |
| D4.1 | Report on implementation of the horizontal measures of the ESRPD | 4 | EDF | R |  |  | PU | 12 | Word document in English |  |
| D4.2 | Report EPSR and the European Semester | 4 | EDF | R |  |  | PU | 12 | Word document in English |  |
| D4.3 | Report on independent living and DI | 4 | EDF | R |  |  | PU | 12 | Word document in English |  |
| D4.4 | Report on improving accessibility in the EU | 4 | EDF | R |  |  | PU | 12 | Word document in English |  |
| D4.5 | Report on disability rights in international cooperation and humanitarian action. | 4 | EDF | R |  |  | PU | 12 | Word document in English |  |

#### Work Package 5

| Work Package 5: Dissemination and communication |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  |  | M1 – M12 |  | Lead Beneficiary: |  | EDF |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |  |
| Ensuring that the general public, EDF members and partners, policy makers, and the media are aware of the outcomes of EDF’s work and are engaged and informed on key issues related to disability rights in Europe. |  |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |
| Task No (continuous numbering linked to WP) |  | Task Name |  |  |  | Description |  | Participants |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  |  |  | Name | Role (COO, BEN, AE, AP, OTHER) |  |
| T5.1 | Annual communication plan |  |  | Overall 2025 internal and external communication plan |  |  |  | EDF | COO | No |
| T5.2 | Managing and updating the current EDF website and members area |  |  | Keep website updated; New page on Disability Rights Strategy and the Review of the EU by the CRPD Committee, updated page on EU Presidencies, passenger rights, legal capacity and supported decision-making, amongst others. Creating and uploading news and blog articles. |  |  |  | EDF | COO | No |
| T.5.3 | Developing a new and improved EDF website |  |  | Start the development of a new EDF website that incorporates accessibility, user interface and design practices that cannot be improved in the current website, as well as enhances the experience for members through a new EDF intranet |  |  |  |  |  |  |
| T5.3 | Newsletters: Disability Voice, Women’s Voice, Global Action |  |  | Provide thematic information and reaching citizens with disabilities and allies through our newsletters; Women’s Voice, Global Action, Disability Voice newsletter on topics relevant to disability rights such as youth, older persons, LGBTQI persons with disabilities,etc. |  |  |  | EDF | COO | No |
| T5.4 | Social media campaigning |  |  | Continue to reach out and stay active. Channels include Twitter, Instagram, Facebook, LinkedIn and other emerging channels. |  |  |  | EDF | COO | No |
| T5.5 | Disability rights in the news: Press and media |  |  | Connecting with press and media (both mainstream and disability specific), publish press releases, liaise with journalists. |  |  |  | EDF | COO | No |
| T5.6 | Top campaigns |  |  | Including topics such as update of the European Disability Rights Strategy 2021-2030, Passenger Rights, accessibility , or “My rights in the EU”. |  |  |  | EDF | COO | No |
| T5.7 | EDF Annual Report 2024 |  |  | Accessible annual report |  |  |  | EDF | COO | No |
| T5.8 | European Human Rights report |  |  | Launch and dissemination of 9th Human rights report on Passengers’ Rights |  |  |  | EDF | COO | No |
| T5.9 | EDF alternative report to the CRPD Committee |  |  | Launch and dissemination of EDF alternative report to the CRPD Committee |  |  |  |  |  |  |
| T5.10 | European awards and competitions |  |  | Cooperate with the European Commission on the Access City Award, EDF Human Rights Photo competition on accessible travel and tourism, freedom of movement, European Toy Manufacturers Awards (Empowerment Category). |  |  |  | EDF | COO | No |
| T.5.11 | Internal communication |  |  | Weekly, members receive the internal newsletter (“Re:Member”); analysis of use and readership of newsletter; Members areas developed and updated. |  |  |  | EDF | COO | No |

|  | Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification |  |  |  |  |  |
| No | Deliverable Name | Work Package No | Lead Beneficiary | Type |  |  | Dissemination Level | Due Date (month number) |  | Description (including format and language) |
| D 5.1 | EDF Annual Report 2024 | 5 | EDF | R |  |  | PU | 12 | Word document in English |  |
| D 5.2 | Communication outputs 2025 | 5 | EDF | R |  |  | PU | 12 | Word document in English |  |
| D5.3 | 9th Human Right Report on Passengers‘ Rights and draft of 10th Human Rights Report on Assistive Technologies | 5 | EDF | R |  |  | SEN | 12 | Word document in English |  |

#### Work Package 6

| Work Package 6: International Cooperation and Humanitarian Action |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  | M1 – M12 | Lead Beneficiary: |  |  | EDF |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |
| - Persons with disabilities are included in new and revised EU external action policies and initiatives and new priority areas are identified. - Persons with disabilities and their representative organisations in all their diversity are meaningfully involved in all EU external action-related policies and democratic decision-making processes within the context of international cooperation, humanitarian action, disaster risk reduction, climate action and the conflict in Ukraine |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |
| Task No (continuous numbering linked to WP) | Task Name |  |  | Description |  |  | Participants |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  |  | Name | Role (COO, BEN, AE, AP, OTHER) |  |
| T6.1 | Ensuring a CRPD perspective in the international work of the next Multiannual Financial Framework (MFF) of the EU |  |  |  | Advocate for a disability inclusive MFF in the relevant policy areas, including Neighbourhood, Development and International Cooperation Instrument, European Civil Protection and Humanitarian Aid Operations, Ukraine Facility, etc. |  | EDF | COO | No |
| T6.2 | Ensuring a global action dimension in the European Disability Rights Strategy ( Articles 11 and 32 of the CRPD) |  |  |  | Collaborate with the European External Action Service (EEAS), relevant DGs such as DG INTPA and DG ECHO, and EU delegations to ensure the implementation of international cooperation aspects of the ESRPD (chapter 6) including in the fields of international development, humanitarian action, climate action, assistance and future reconstruction of Ukraine, disaster risk reduction. |  | EDF | COO | No |
| T6.3 | Ensuring a CRPD perspective and mainstreaming the rights of persons with disabilities in the EU External Action Plan on Human Rights and Democracy |  |  |  | Collaborate with the European External Action Service (EEAS), Human Rights and Democracy Network (HRDN) and EU delegations to ensure a disability inclusion in EU Human Rights Dialogues with partner countries. |  | EDF | COO | No |
| T6.4 | Ensuring EU Official Development Assistance (ODA) projects are both mainstreaming persons with disabilities and targeting persons with disabilities |  |  |  | Collaborate with EU institutions to increase the number of EU ODA projects that are inclusive of persons with disabilities. |  | EDF | COO | No |
| T6.5 | Follow up and engage on regional and international events 2024/2025 (such as European Regional Disability Summit 2024, European Humanitarian Forum, Global Disability Summit 2025, CoP29) |  |  |  | Several high-level events related to disability-inclusive development, humanitarian action and climate action will take place in both 2024 and 2025 and EDF will participate and follow up to ensure disability-inclusive development in the years to come. |  | EDF | COO | No |

| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification |  |  |  |  |  |
| Deliverable No (continuous numbering linked to WP) | Deliverable Name | Work Package No | Lead Beneficiary | Type |  |  | Dissemination Level | Due Date (month number) |  | Description (including format and language) |
| D6.1 | Report on disability rights in international cooperation and humanitarian action. | 6 | EDF | R |  |  | PU | 12 | PDF document in English |  |
| D6.2 | DAC Disability Marker Report | 6 | EDF | R |  |  | RU | 12 | Word document in English |  |

#### Work Package 7

| Work Package 7: List of EDF projects |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  | M1 – M12 | Lead Beneficiary: |  |  | EDF |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |
| - Give an overview of all projects that EDF will be involved in during 2025 (projects started before 2025 and those that we know will start during the year) - Show the breadth of EDF engagement on different topics that are not covered by the EU grant - More details about each project can be found on the EDF website: https://www.edf-feph.org/projects/ |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |
| No | Project Name |  |  | Description |  |  | Participants |  | Funded by |
|  |  |  |  |  |  |  | Name | Role (COO, BEN, AE, AP, OTHER) |  |
| 1 | HEALTH research: increasing access to healthcare for persons with disabilities (2023 – 2025) |  |  |  | Support EU Member States, Iceland and Norway with guidance on increasing access to healthcare for persons with disabilities, with a focus on cancer care. |  | EDF (subcontractor), ICF (lead) | Other COO | EU4Health Programme (EU) |
| 2 | Accessible Spaces For All: Improving Accessibility of Tourism for Persons with Disabilities in Central Europe (01 March 2023 to 28 February 2026) |  |  |  | Improve governance and cooperation of multi-level cross-sectoral stakeholders for better territorial planning and implementation of accessible tourism for persons with disabilities in rural border regions in Central Europe. |  | EDF | Advisory board | INTERREG Central Europe (EU) |
| 3 | AccessibleEU Centre (2023 – 2026) |  |  |  | AccessibleEU is a resource centre on accessibility, working in the areas of built environment, transport, information and communication technologies, and accessibility policies, to ensure the participation of persons with disabilities in all areas of life on an equal basis with others. |  | EDF | Advisory board | EU |
| 4 | Disability Inclusive Artificial Intelligence (AI) – Continuation (11.2024 – 12.2025) |  |  |  | Advocating for the rights of persons with disabilities in relation to the development and use of AI technologies; expand the knowledge of the European disability rights movement. |  | EDF | COO | European AI and Society Fund |
| 5 | ATHENA - Bringing Accessibility and Design for All into Higher Education Curricula (01.2023-06.2025) |  |  |  | ATHENA project aims to bring Accessibility and Design for All into Higher Education Curricula by developing and testing guidelines and recommendations which will stimulate innovative learning and teaching practices to tackle social inclusion of persons with disabilities. |  | EDF | COO | Erasmus |
| 6 | European disability expertise (2024-2027) |  |  |  | The aim of EDE is to collect, analyse and provide independent scientific data and information relating to national policies and legislation, linked with provisions at EU level, as well as providing information about the situation of persons with disabilities. |  | EDF, Human European Consultancy | Expert | EU |
| 7 | “Empowered by AI” - AI for Accessibility, Inclusion and Rights of persons with disabilities (01.2025 - 12.2027) |  |  |  | To solve the problem of lack of data on the topic of AI and disability EDF will conduct a research to identify the implications of AI on persons with disabilities. |  | EDF | COO | Google.org |
| 8 | EMPOWER- inclusive humanitarian action in with our Ukrainian members National Assembly of Persons with Disabilities (NAPD) and the League of Strong, in cooperation with CBM International |  |  |  | To provide ongoing support to persons with disabilities and their organizations in Ukraine |  | EDF as implementing partner; CBM International lead | BEN | GFFO |
| 9 | Nothing without us: Women with disabilities leading the change |  |  |  | Improvement in the inclusion and active participation of women with disabilities within the disability rights and feminist movements. This includes the establishment of women's committees, adoption and implementation of gender equality mainstreaming tools, and financial support for women's rights work at various levels. |  | EDF lead | COO | Fondation Chanel |
| 10 | Energy Performance of Buildings Directive (EPBD) |  |  |  | To ensure that newly renovated or built buildings are energy efficient and accessible to persons with disabilities. |  | EDF lead | COO | European Climate Foundation |
| 11 | ACT4DYS-Enable people with disabilities and youth to act for sustainable cities |  |  |  | Project aims to build youth workers and young people's capacity in sustainable and inclusive urban development and empower them to take action to improve sustainability and inclusivity in urban communities. |  | EDF as partner | Partner | Erasmus |
| 12 | Wellspring operating grant |  |  |  | Inclusion of persons with disabilities in the European Union's global work: EDF programme 2024-2025 |  | EDF as lead | COO | Wellspring Philanthropic Found |