DOC-EXEC-25-09-03

# Update on EDF role in projects

Document for information and decisions

Update on EDF role in projects	1

Introduction and purpose	2

Questions for the Executive Committee for the decision	2

Comments for the Executive Committee	2

Annex 1. Submitted applications, waiting for results (do not require decisions)	3

1.	Additional 5000 for AI project for 2025-2026	3

2. Disability-inclusive AI 3 (EDF as coordinator)	3

3	Autonomy, Inclusion, And Mobility For Persons With Disabilities (EDF as a partner)	3

4. Fostering Autonomy and Inclusion of People with Disabilities in Education, Work and Retirement (EDF as a partner)	4

5. Inclusive Healthcare Accessibility: Enhancing Autonomy and Inclusion for Persons with Disabilities (EDF as a partner)	4

6. Develop, Exercise and Maximise Autonomy for Disabled People in Europe (EDF as a partner)	5

7. Improving Access to Healthcare for Migrants with Disabilities (EDF as coordinator)	6

8. Digital Skills for Migrants with Disabilities (EDF as coordinator)	6

9. CBM Advocacy project (EDF as lead)	7

10. READY BATICS	7

11. Strengthening the disability climate action caucus – grant 2	8

12. Disability Inclusive Emergency Preparedness and Response	9

Annex 2. Update on European ongoing projects (do not require decisions)	10

1.	YO-IN Youth Organisations for Inclusion (EDF as a coordinator)	10

2.	KEEP Driven: Fostering Knowledge, Empowerment, and Participation of Youth with Disabilities (EDF as a partner)	10

3.	Nothing without us: Women with disabilities leading the change (EDF as a coordinator)	11

4.	“Empowered by AI” - AI for Accessibility, Inclusion and Rights of persons with disabilities (EDF as coordinator)	12

5.	Accessible Spaces for All (EDF as a partner)	13

6.	Disability-inclusive AI 2 (EDF as coordinator)	14

7.	Energy Performance of Buildings Directive (EPBD)	14

8.	Wellspring International cooperation (Operating general support grant)	15

9.	Ukraine programme (EDF as Coordinator)	15

10.	Strengthening the disability climate action caucus	16

11. Wellspring last operating grant	16

## Introduction and purpose

This document presents an overview of projects and applications for projects that EDF is involved in.

## Questions for the Executive Committee for the decision

- Who will be the focal point from the Executive for the new youth project, starting in December, YO IN?

## Comments for the Executive Committee

The Secretariat would like to bring to your attention that Wellspring will provide its final General Operating Grant in 2026. After that, we will no longer receive support for the work of the International Cooperation Team unless new sources of funding are secured, and participation in international meetings will only be possible if specific funding is available for each meeting.

Annex 1. Submitted applications, waiting for results (do not require decisions)

## Additional 5000 for AI project for 2025-2026

To cover reasonable accommodation and training for EDF staff.

## 2. Disability-inclusive AI 3 (EDF as coordinator)

Funder: European AI Fund

Duration of the project: 24 months (01.01.2026 - 31.12.2027)

Budget of the project: 200,000 euro

Budget of EDF: 200,000 euro

Co-financing: n/a

Results: November 2025

Activities of EDF:

- Policy work on AI

- Developing training and capacity building among members on AI

- Report on impact of AI on women with disabilities

- Co-financing to Youth Committee meeting 2027

## 3. Autonomy, Inclusion, And Mobility For Persons With Disabilities (EDF as a partner)

Funder: Horizon Europe

Results: February 2026

Duration of the project: 36 months

Lead: FCIENCIAS.ID

Budget of the project: >3.000.000 euro

Grant for EDF:  404.487 euro

Salaries for EDF:  309.590 euro

Co-financing: n/a

Activities:

- Leading WP4: Policy Innovation Laboratory (LC) Duration: M6-M30

- Major Tasks:

  - T4.1: Policy challenges identification and simulation (M6-M24) (LC)

  - T4.1: Social Hackathons implementation (M13-M36) (KPRF)

  - T4.2: Assistive policy identification, simulation and validation (M13-M36) (LC)

  - T4.3: Evidence collection and analysis (M18-M36) (H2I)

  - T4.4: Policy briefs and recommendations (M18-M36) (LC)

- Leading 3 more policy related tasks.

## 4. Fostering Autonomy and Inclusion of People with Disabilities in Education, Work and Retirement (EDF as a partner)

Funder: Horizon Europe

Results: February 2026

Duration of the project: 36 months

Lead: The Open University

Budget of the project: >3.000.000 euro

Grant for EDF: 110.187 euro

Salaries for EDF:  75.250 euro

Co-financing: n/a

Activities:

- WP1

  - Create a contact between academics and your members organisation – to facilitate recruitment of interviewees (this across WPs and in particular WP1, WP5,WP6)

  - Mapping the list of policies around digital transition and disability at EU level – creating a list of policies at EU level and put academics in contact with policy makers for interviews

- WP2

  - Send a Qualtrics survey to your members (just send it) for collecting AI software (put basically the news of the survey in a mailing list)

- WP6

  - Supporting the organisation of FUTURO Policy Forum for the manifesto (leader SOLIDAR)

  - Leading the organisation of a Policy Workshop  in Bruxelles– last small and policy oriented event to disseminate manifesto

## 5. Inclusive Healthcare Accessibility: Enhancing Autonomy and Inclusion for Persons with Disabilities (EDF as a partner)

Funder: Horizon Europe

Results: February 2026

Duration of the project: 36 months

Lead: ISTINYE UNIVERSITY

Budget of the project: >3.000.000 euro

Grant for EDF:  433.125 euro

Salaries for EDF:  301.500 euro

Co-financing: n/a

Activities:

- WP2- Policy Mapping and Legal Landscape Analysis: Co-lead in comparative healthcare policy analysis; supporting the drafting and validation of policy recommendations aligned with the CRPD and EU frameworks. Providing guidance on inclusive assessment tools and contributing to data collection efforts through EDF’s member networks.

- WP4 - Inclusive Training for Healthcare Professionals:

  - Strategic advisory input on EU disability policies and inclusion frameworks to ensure alignment with European standards.

  - Contribution to the design and review of inclusive training materials and accessibility indicators from a policy perspective.

  - Leading dissemination activities, including stakeholder outreach through EDF’s network, especially targeting EU-level institutions and advocacy platforms.

  - Facilitation of a high-level closing roundtable to consolidate policy-related outcomes and support future EU policy recommendations.

- WP5- Pilot Implementations and Field Testing: Advising on inclusive and ethical pilot implementation, and helping disseminate pilot results.

## 6. Develop, Exercise and Maximise Autonomy for Disabled People in Europe (EDF as a partner)

Funder: Horizon Europe

Results: February 2026

Duration of the project: 36 months

Lead: UNIVERSITY OF GALWAY

Budget of the project: >3.000.000 euro

Grant for EDF: 532.188 euro

Salaries for EDF:  300.000 euro

Co-financing: n/a

Activities:

- EDF will lead the Technology topic (with Funka Foundation as co-lead) and co-lead the Participation in Political and Public Life topic (led by Benoit Eyraud).

- EDF will also provide input to the development of the app based on their knowledge and expertise and their analysis of overall trends on the technology topic.

- EDF will also co-ordinate a Disabled People’s European Assembly for this project.

## 7. Improving Access to Healthcare for Migrants with Disabilities (EDF as coordinator)

Funder: AMIF

Results: February 2026

Duration of the project: 26 months

Lead: EDF

Budget of the project: 1.893.151 euro

Grant for EDF:  303.880 euro

Salaries for EDF: 215.800 euro

Co-financing: 10%

Members as partners: Idein, CBm Italia, LEDHA, Newcomesrs wth disabilities in Sweden

Activities:

- Building capacity for better access to healthcare services for migrants with disabilities

- Targeted outreach to migrants with disabilities

- Exchange of learning & awareness raising

## 8. Digital Skills for Migrants with Disabilities (EDF as coordinator)

Funder: AMIF

Results: February 2026

Duration of the project: 26 months

Lead: EDF

Budget of the project: 1.168.333 euro

Grant for EDF:  253.461 euro

Salaries for EDF: 215.800 euro

Co-financing: 10%

Members as partners: Idein, CBm Italia, LEDHA, Newcomesrs wth disabilities in Sweden

Activities:

- Creation of Digital Resource Library and Training Material

- Capacity-building and Training of Trainers (ToT)

- Exchange of Learning, Awareness, and Dissemination

## 9. CBM Advocacy project (EDF as lead)

Funder: CBM International

Results: October 2025

Duration of the project: 12 months

Lead: EDF

Budget of the project: 125 000 euro

Grant for EDF:  125 000 euro

Salaries for EDF: 80 000 euro

Co-financing: None

Members as partners: None

Activities:

- Disability-Inclusive EU External Action and Policy Engagement

- Disability-Inclusive Preparedness and Response

- Disability-Inclusive DRR

- Donor Accountability and Inclusive Funding

- Movement Support and Regional OPD Coordination

## 10. READY BATICS

Funder: ECHO (Knowledge for Action in Prevention & Preparedness: 2025 call for proposals)

Results: October 2025

Duration of the project: 24 months

Lead: EDF

Budget of the project: Under 1 099 878.68 Euro

Grant for EDF:  434 740.56 Euro

Salaries for EDF: 282 000 Euro

Co-financing: 10% own resources (48 304.52 Euro)

Members as partners: EPIK (Estonia), Sustento (Latvia) and LNF (Lithuania)

Activities:

- Work Package 1: Project management, coordination and communication

- Work Package 2: Review of disability inclusion in DRM policy and practice

- Work Package 3: Development of training tools, conducting trainings and capacity building of OPDs and civil protection/DRM professionals

- Work Package 4: Conducting multi-stakeholder workshops and assessing the disaster resilience and accessibility of cities

- Work Package 5: Advocacy and resource building at individual, local/national, regional and international levels

## 11. Strengthening the disability climate action caucus – grant 2

Funder: Disability Rights Fund (DRF)

Results: October 2025

Duration of the project: 6 months

Lead: EDF

Budget of the project: 34382.40 US dollars

Grant for EDF:  34382.40 US dollars

Salaries for EDF: 2 months February and March 2026 (This grant is a complement to the current DRF climate project, which already covers one salary from August 2025 to January 2025)

Co-financing: None

Members as partners: None

Activities:

- Advocate for disability inclusion in climate policies

- Support meaningful participation of persons with disabilities at COP30

- Strengthen the Disability Climate Action Caucus

## 12. Disability Inclusive Emergency Preparedness and Response

Funder: World Bank (Global Facility on Disaster Risk Reduction), with funding from ECHO

Results: October 2025

Duration of the project: 12 months

Lead: EDF

Budget of the project: 35000 Euro

Grant for EDF:  35000 Euros

Salaries for EDF: None.

Co-financing: None

Members as partners: None

Activities:

- Diagnostic and Stakeholder Mapping (with support from consultant)

- Guidelines review

- Curriculum review

# Annex 2. Update on European ongoing projects (do not require decisions)

## YO-IN Youth Organisations for Inclusion (EDF as a coordinator)

Call: Erasmus +, Strategic partnership

Duration: 24 months (1.12.2025 – 30.11.2027)

Project Budget: 400.000

EDF budget: 152.135 euro

EDF staff budget: 129.800

Objective of the project:

YO-IN project aims to improve the management of European youth organisations with regard to inclusion and accessibility of persons with disabilities, by encouraging and recognizing the efforts of organisations that choose to implement disability inclusion plans, creating standards and certifications that inspire them to progress and make young people with disabilities more confident and active in the activities and projects of youth organisations.

Project officer: Markaya Henderson

Questions: who will be the focal point in the Executive Committee for this project?

## KEEP Driven: Fostering Knowledge, Empowerment, and Participation of Youth with Disabilities (EDF as a partner)

Funder: Erasmus+

Coordinator: CBM Italy

Partners: SUSTENTO (Latvia), Ledha – Lega per i diritti delle persone con disabilità (LEDHA / FISH), Association APF France handicap (APF)

Duration of the project: 18 months

Dates of the project: 1st April 2025 – 30th September 2026

Budget of the project: 250.000 EURO

Budget of EDF: 84 614 EURO

Salaries for EDF: 49.648 EURO

Co-financing: n/a

Project officer: An-Sofie Leenknecht

EDF’s role:

- Lead of Work Package 1 (knowledge sharing) with the support of CBM and partners, EDF develops the survey and an online dialogue session, facilitating the participation of its members and the involvement of relevant stakeholders i.e. European Youth Forum, and manages accessibility;

- Work Package 2, it facilitates the involvement of its Youth Committee and manages resources (travel, venue, accessibility) for organising the workshop session in Brussels with 30 participants, including Youth Committee members and young people involved by the partners; EDF also contributes to the creation of guidelines by CBM with the partners;

- Work Package 3, it collaborates with partners in implementing an advocacy campaign by providing expert input; facilitates the dissemination of outputs to its members and stakeholders;

Work Package 4, EDF participates in coordination meetings, including 2 in-person meetings.

## Nothing without us: Women with disabilities leading the change (EDF as a coordinator)

Funder: Chanel foundation

Lead: EDF

Duration of the project: 36 months

Dates of the project: 1.12.2024 – 30.11.2027

Budget of the project: 599.270 euro

Salaries for EDF: 283.500 euro

Co-financing: n/a

Subgranting for members: 60.000 euro

Objectives:

- To support organisations of persons with disabilities, at European and national levels, in advocating for women’s rights by creating women’s committees, adopting gender equality and mainstreaming tools, and providing financial support for women's rights initiatives

- To bridge the gap between the disability and women’s rights movements by facilitating workshops and mentorship programs that bring together women leaders with disabilities and representatives from the women’s rights movement, through members of the European Women’s Lobby.

- To support self-advocacy of women with disabilities through leadership and activism training, equipping them with the skills and tools needed to effectively advocate for their rights.

Activities of EDF:

- Strategic support of EDF member organisations

- Sub-granting programme

- Workshops and networking between the disability and women’s rights movements

- Mentorship programme

- European Conference

Project Officer: Giulia Traversi

Executive focal point: Pirkko Mahlamaki

## “Empowered by AI” - AI for Accessibility, Inclusion and Rights of persons with disabilities (EDF as coordinator)

Lead: EDF

Results: October 2024

Budget:: 700.000 euro

Salaries: 300.000 euro tbc

Subgranting for members: 100.000 euro

Duration: 24 months (11.2024 – 10.2026)

Activities:

1. Empowered by AI” - Program for EDF secretariat and its Members

  - Creation of the program of empowering EDF and Members in areas of:

    - Increasing understanding what is AI among persons with disabilities – starting from EDF and its Members

    - Assessing the range of AI tools available for the accessibility, usefulness, privacy and safety for persons with disabilities and their organisations

    - Assessing the impact of AI in the implementation of accessibility-related policies (e.g. Web Accessibility Directive, European Accessibility Act, Audiovisual and Electronic Communications legislations)

    - Improving internal tools and introduction of new AI tools

    - Improving accessibility of meetings (AI in captioning, automated document translations, etc.)

    - Improving monitoring of our work using AI - for example by creating more automated smart systems for monitoring impact of our advocacy, capacity building and communications, measuring our environmental footprint, understanding the diversity of our audience

    - Testing AI solutions and tools for inclusion and accessibility

  - Training for EDF staff and Members

- White paper on AI (with significant part on AI, will include results of the research)

- Capacity building for EDF members – subgranting to support EDF members self-directed action in the field of AI

Project Officer: Roberta Lulli

Executive focal point:

## Accessible Spaces for All (EDF as a partner)

Funder: Interreg Central Europe Programme 2021-2027

Lead: Geodetic Institute of Slovenia

Duration of the project: 36 months

Dates of the project: 1.03.2023 – 28.02.2026

Budget of the project: 2,509,718 euro

Budget of EDF: 201,600 euro

Salaries for EDF: 144,000 euro

Co-financing: 20%

Project officer: An-Sofie Leenknecht

Exec focal point: Gunta Anca

Activities of EDF: Policy recommendations, support in testing of solutions, organising final project conference in Brussels on 27th November 2025.

Project officer: An-Sofie Leenknecht

## Disability-inclusive AI 2 (EDF as coordinator)

Funder: European AI Fund

Duration of the project: 24 months (01.11.2022 - 31.12.2025)

Budget of the project: 185,600 euro

Budget of EDF: 185,600 euro

Co-financing: n/a

Project Officer: Kave Nori (with support of Magdalena Verseckas and Marine Uldry)

Exec focal point: Maureen Piggot & Vera Bonvalot

Activities of EDF:

- Policy work on AI

- Developing campaign on AI

- Developing training and capacity building among members on AI on AI

- We co-financed the Board meeting in Sweden in spring 2023

- We implemented subgranting programme for Members and we have 9 grantees.

## Energy Performance of Buildings Directive (EPBD)

Funder: European Climate Foundation

Duration of the project: 12 months (01.11.2024 - 30.10.2025)

Budget of the project: 50,000 euro

Budget of EDF for salaries: 32,640 euro

Co-financing: n/a

Project Officer: Magdalena Verseckas

Activities of EDF:

- Campaign on Energy Performance of Buildings Directive

## Wellspring International cooperation (Operating general support grant)

Title: Inclusion of persons with disabilities in the EUs global work: EDF programme 2024-2025

Donor and timeframe: Wellspring Philanthropic Trust; 1 March 2024 to 28 February 2026 (2 years)

Total budget and EDF budget: US $450.000. It is an operating grant, which includes $50000 for our Ukraine work.

Objective of the project: The EU becomes a global leader in disability inclusive development, with DPOs actively and meaningfully involved in international cooperation and humanitarian action.

Partners (if any): None.

EDF role: Implementation of the general operating grant based on two short-term outcomes – 1) EU global policies, programmes and budgets are increasingly disability inclusive;  2) Capacity of EDF members and partner regional DPOs is strengthened to engage in policy and programme dialogue with the EU including its overseas delegations, in international cooperation and humanitarian action.

EDF staff involved: Marion Steff

Exec focal point: Nadia Hadad

Current activities, foreseen outcomes, successes: This grant supports the operating work of the international team, with no specific deliverables required from the donor.

## Ukraine programme (EDF as Coordinator)

Title: Ukraine programme

Overview:

By September 2025, 18,938 people and their families have been supported through the Empower Ukraine project. 13,202 of these are persons with disabilities. €1,040, 000 has been distributed as cash, and more than 2500 people trained on disability inclusion in various areas.

The funding currently totaling 4,5 million is from contributions from CBM International and the German Foreign Federal Office (GFFO). In October 2025 we submit a request for a 5- month extension for 444,444 €. In 2026 there are invitations for EDF to continue to extend the work but focused on advocacy and not project coordination.

Donor and timeframe:

- GFFO – Sept 2023 – Dec 2025 (€4,5 million committed)

- Invitation to extend to May 2026 (additional €444,444)

- Invitation to submit for new project GFFO funded dates and amounts pending

Total budget for EDF and partners:

- CBM- GFFO, Empower programme: 4.500.000,00 EUR

Overview: Empower Ukraine is the German Foreign Federal Office funded portion of the Ukraine programme.

Partners (if any): Ukraine – National Assembly and League of the Strong.

EDF role:  Project coordination and donor liaison, Capacity building of members and Advocacy at EU and International level

EDF staff: Phillipa Tucker, Kateryna Ostashkova and Mariya Yasenovska

Exec focal point: Gunta Anca

Current activities, foreseen outcomes, successes: See our website page.

## Strengthening the disability climate action caucus

Donor and timeframe: Disability Rights Fund; 1 August 2025 to 31 January 2026 (6 months)

Total budget and EDF budget: 57 800 Euros

Objective of the project:

Partners (if any): IDA (no financial support to IDA)

EDF role: Strengthen the disability climate action caucus

EDF staff involved: Marion Steff

Exec focal point: Nadia Hadad

- Current activities, foreseen outcomes, successes: Advocate for disability inclusion in climate policies

- Support meaningful participation of persons with disabilities at COP30

- Strengthen the Disability Climate Action Caucus

## 11. Wellspring last operating grant

Donor and timeframe: Wellspring Philanthropic Trust; 1 December 2025 to 31 December 2026 (1 year)

Total budget and EDF budget: US $351,865. It is an operating grant.

Objective of the project: Final award for General Operating Support focusing on supporting the work of the international cooperation team.

Partners (if any): None.

EDF role: Implementation of the general operating grant based on two short-term outcomes – 1) EU global policies, programmes and budgets are increasingly disability inclusive;  2) Capacity of EDF members and partner regional DPOs is strengthened to engage in policy and programme dialogue with the EU including its overseas delegations, in international cooperation and humanitarian action.

EDF staff involved: Marion Steff

Exec focal point: Nadia Hadad

Current activities, foreseen outcomes, successes: This grant supports the operating work of the international team, with no specific deliverables required from the donor.