# Annex to DOC 26-02-03 risk review  Overview of full organisational risks

| Date identified | Risk type | Likelihood | Severity | Ownership | Measures |
| --- | --- | --- | --- | --- | --- |
| 2025 | Marked decreased of funding for human rights/social issues NGOs – it can affect us and also increases competition to existing funding/sponsorships | High | High | Executive and Director | Continue funding diversification Maintain good relationship with current donors + continue to diversify Manage costs with discipline Perfect management of current grants |
| 2025 | Hacking of our online events | High | High | Communications manager | Introduce raft of security improvements in our online events, external expertise + training |
| 2025 | Death or illness at one of our events | Medium | Medium | Executive Director | Thorough registration of contact details, safely information for Delegates, Adequate staffing at our events |
| 2025 | Inadequate financial reserve – EDF does not have an adequate reserve to ensure it could close its operation if needed | High | Medium | Executive | Develop reserve policy and build up adequate reserves |
| 2025 | Secretariat is understaffed for operations; no operation manager, events coordinator, executive secretary- and no internal finance expert- thus we are relying on the external accountant: consequent overuse of time of other staff for these tasks + these tasks less well done, or outsourced expensively | High | Medium | Executive and Director | Recruitment of Operations manager with finance/accounting background once it is safe to do so (once CERV is approved) External HR support Build operations staffing funds into projects more comprehensively |
| 2025 | Decreased confidence of team due to sustained pay freeze and other measures to cut costs | Medium | Medium | Executive and Director | Reinstate regular PayScale in January |
| 2025 | Reputational risk with companies reducing human rights commitments | High- see announcements from Meta and Amazon | To be assessed | Executive | Review Corporate Sponsorship Policy, reassess partnerships |
| 2019 | Website security | High | High | Communications Manager | New website development with Funka |
| 2022 | Members not aligned to CRPD | Likely | Moderate | Executive | Monitor, report issues to executive |
| 2015 | Mission creep | Likely | Moderate | Executive Director/Executive | Careful work planning, regular meetings, do not take on things outside of our strategy |
| 2015 | Financial situation/funding decreases | Moderate | High | Executive Director | Manage finances, fundraise |
| 2021 | Loss of EU funding | Moderate | High | Executive Director | Prepare workplan, advocate EU budget |
| 2025 | Loss of member funding and advocacy capacity | High | Moderate/High | Executive Director/Sr. Policy Coordinator | Facilitate peer exchanges, focus on subgranting |
| 2025 | Eroding disability rights due to political shifts | Very High | High | Executive Director/Executive | Track politics, increase public campaigns, build member capacity |
| 2025 | Disability Unit move to DG Justice | Moderate/Low | Moderate | Executive Director/Head of Policy | Engage with new Commissioners and DG JUST, strengthen contacts |

| Date identified | Risk type | Likelihood | Severity | Ownership | Measures |
| --- | --- | --- | --- | --- | --- |
| 2025 | Marked decreased of funding for human rights/social issues NGOs – it can affect us and also increases competition to existing funding/sponsorships | High | High | Executive and Director | Continue funding diversification Maintain good relationship with current donors + continue to diversify Manage costs with discipline Perfect management of current grants |
| 2025 | Hacking of our online events | High | High | Communications manager | Introduce raft of security improvements in our online events, external expertise + training |
| 2025 | Death or illness at one of our events | Medium | Medium | Executive Director | Thorough registration of contact details, safely information for Delegates, Adequate staffing at our events |
| 2025 | Inadequate financial reserve – EDF does not have an adequate reserve to ensure it could close its operation if needed | High | Medium | Executive | Develop reserve policy and build up adequate reserves |
| 2025 | Secretariat is understaffed for operations; no operation manager, events coordinator, executive secretary- and no internal finance expert- thus we are relying on the external accountant: consequent overuse of time of other staff for these tasks + these tasks less well done, or outsourced expensively | High | Medium | Executive and Director | Recruitment of Operations manager with finance/accounting background once it is safe to do so (once CERV is approved) External HR support Build operations staffing funds into projects more comprehensively |
| 2025 | Decreased confidence of team due to sustained pay freeze and other measures to cut costs | Medium | Medium | Executive and Director | Reinstate regular PayScale in January |
| 2025 | Reputational risk with companies reducing human rights commitments | High- see announcements from Meta and Amazon | To be assessed | Executive | Review Corporate Sponsorship Policy, reassess partnerships |
| 2019 | Website security | High | High | Communications Manager | New website development with Funka |
| 2022 | Members not aligned to CRPD | Likely | Moderate | Executive | Monitor, report issues to executive |
| 2015 | Mission creep | Likely | Moderate | Executive Director/Executive | Careful work planning, regular meetings, do not take on things outside of our strategy |
| 2015 | Financial situation/funding decreases | Moderate | High | Executive Director | Manage finances, fundraise |
| 2021 | Loss of EU funding | Moderate | High | Executive Director | Prepare workplan, advocate EU budget |
| 2025 | Loss of member funding and advocacy capacity | High | Moderate/High | Executive Director/Sr. Policy Coordinator | Facilitate peer exchanges, focus on subgranting |
| 2025 | Eroding disability rights due to political shifts | Very High | High | Executive Director/Executive | Track politics, increase public campaigns, build member capacity |
| 2025 | Disability Unit move to DG Justice | Moderate/Low | Moderate | Executive Director/Head of Policy | Engage with new Commissioners and DG JUST, strengthen contacts |