[image: image1.jpg]Funded by
the European Union




[image: image2.png]EUROPEAN
DISABILITY

FORUM






   
DOC-EXEC-26-02-09
Annex to 2026 Planning – Full 2026 Work Plan
                                 Document for information 
2026 Work Plan

Work Package 1

	T1.1
	Annual General Assembly (AGA)

(held simultaneously with Executive committee, Board, and selected trainings and workshops)
	European gathering of all members of EDF to make decisions, engage in EU and national level policy dialogue and create collective joint advocacy. In 2026, EDF will elect a new Board and Executive Committee. We plan to hold the event in Cyprus (tbc) and there will be a joint conference on persons with disabilities with the Cypriot Council Presidency. 

	T1.2
	Board meetings 

(accompanied by committee meetings, workshops and conferences, for organisational and economic reasons)
	Meeting of the 31 elected members of the EDF Board, persons with diverse disabilities from across Europe. Board meetings are planned for Spring 2026 online and Autumn in Ireland (tbc). The Autumn Board meeting will focus on introducing the new Board members following the elections at the Annual General Assembly.

	T 1.3
	Executive Committee meetings
	Meeting of the 11 elected members of the Executive committee of EDF, 5 times per year. In 2026 these are planned to take place in Brussels, Cyprus, Luxembourg (tbc), amongst others, and are co-organised with our members.

	T 1.4
	Good governance and accountability 
	EDF policies are up to date (see Annex XY – Register of EDF organisational policies and guidance) and EDF continues implementing its organisational strategy adopted in 2024. This includes for example establishing the Diversity and Inclusion Committee. 

	T 1.5
	Risk management 
	In-depth risk-review taking into account the current political situation as well as internal changes in the organisation.

	T 1.6
	Monitoring and evaluation 
	Regular monitoring with a gender and diversity dimension across all of EDF’s work. This will be done by evaluating all our events with designated members as evaluators, collecting data about diversity of our audiences, and reporting in our custom-made reporting tool including quantitative and qualitative data. 

	T 1.7
	Financial management 
	Continue the thorough restructuring and strengthening of our financial management system, monitoring, financial planning, and strategy. Regular accounting, quarterly financial reports to the Executive and biannual reports to the Board. 2025 accounts audited and submitted to the AGA. Revision of EDF Procurement Policy.

	T 1.8
	Financial sustainability- fundraising and income diversification 
	Continuing the implementation of fundraising diversification plan with a focus on undesignated funding. Increase our efforts on relationship building and proposals to new sponsors, foundations, donors, and project development.

	T 1.9
	Human resource management 
	Continue strengthening our HR management system through investment in tools, processes, and training. Annual staff survey to give feedback to Management Team. Annual staff training programme including training on EU institutions and decision-making, Human Resources, communication skills, etc.

	T 1.10
	Membership 
	Introduce regular membership survey; Assess applications of potential members; Welcome and train new members and their staff once their applications are approved. Regular coordination meetings with EU-level members and national members to better involve them in our advocacy work. Ensure that the database with members’ contacts is up to date and assess the benefits and accessibility of using a new CRM system.

	T 1.11
	IT infrastructure and security
	Ensure continued IT security with our new IT provider and consolidate our new online working environment on SharePoint.


Work Package 2

	T 2.1
	Training and guidance on national transposition and implementation of EU legislation that concern persons with disabilities
	Including webinars, workshops, and supporting documents on strategic litigation, the European Disability Card, victims’ rights (once adopted), passengers’ rights…

	T 2.2
	Training and guidance on new and on-going policy initiatives and developments that concern persons with disabilities
	Including webinars, workshops, and supporting documents on the next Multiannual Financial Framework (MFF), housing, climate action, rail accessibility, new actions under the EU Disability Strategy (if released); new equality strategies (LGBTI, Gender, Anti Racism) and intersectionality with disability rights, inclusive education for learners with disabilities, access to healthcare, asylum and migration…

	T 2.3
	Supporting EDF members whose Member States are undergoing review by the CRPD committee 
	Reviewing draft Alternative Reports, preparing EDF members for the sessions of the UN CRPD Committee through online or in person trainings, responding to ad-hoc questions of members on national and European CRPD review. Countries for review (tbc): Bosnia, Croatia, Czechia, Ireland, Lithuania, Romania, Slovakia

	T 2.4
	Supporting EDF members undergoing review by the UN Committee on Elimination of Discrimination Against Women (CEDAW) and the Council of Europe’s Groups of Experts on Action against Violence (GREVIO)
	Reviewing the draft Alternative Reports, preparing EDF members for the sessions of the UN CEDAW Committee or meetings with GREVIO, and responding to ad-hoc questions of members in the context of the review. 

	T 2.5
	Capacity building series for EDF members on organisational development for Organisations of Persons with Disabilities (OPDs)
	Trainings to increase organizational capacity of members and peer exchange of funding sources and functioning of national OPDs. In 2026, we will organise trainings on the use of Artificial Intelligence tools, diversity and inclusion, project management, fundraising, etc.  

	T 2.6
	Facilitate peer exchange between EDF members
	Online and face to face sessions on topics such as EU Presidencies, the Accessibility Act and its standardisation developments, the European Disability Card; Using disability data and statistics for advocacy; work with national CRPD monitoring mechanisms; transposition of the EU directive on combating violence against women.  

	T 2.8
	Training for new EDF Board and Executive members
	Following the EDF elections in in May 2026, we will have new Board members who will need to receive training on their new job. This training will include EDF internal rules for external representation, the functioning and internal policies of EDF, responsibilities of Board members, etc.

	T 2.9
	Training for EDF members on communications
	Practical training session for EDF members on accessibility of communications, campaigning and communications trends and tools.


Work Package 3

	T 3.1
	Mainstreaming the CRPD in all EU legal and policy initiatives, as well as in institutional structures of the EU institutions and in meetings with EU decision-makers.
	Monitor legislation and polices to ensure compliance with CRPD and increase the diversity of voices representing EDF in EU policy making. Give feedback via official EU channels: roadmaps, public consultations, hearings, stakeholder meetings, etc. 

	T 3.2
	Ensuring participation of persons with disabilities in EU Council Presidencies
	Publication and dissemination of EDF’s top 10 priorities for the next Presidency TRIO; Meetings with national decision-makers and Presidency representatives; Involvement in EU Presidency events on disability wherever possible; Implementation of the “Presidency Scorecard” system that was developed in 2024 to assess the inclusiveness of the Cypriot and Irish EU Presidencies.

	T 3.3
	Ensuring a CRPD perspective in the next Multiannual Financial Framework (MFF) of the EU 
	Advocate for a disability inclusive MFF in the relevant policy areas, including the Citizens, Equality, Rights, and Values Programme (CERV) in collaboration with Civil Society Europe, EU structural and investment funds in relation to independent living, accessibility, social inclusion in collaboration with Social Platform, and other relevant funding programmes. 

	T 3.4
	Follow up to the EU review by the UN Committee on the Rights of Persons with Disabilities (CRPD) and participation at the CRPD Monitoring Framework
	Ensure that the EU Strategy on the Rights of Persons with Disabilities addresses the Concluding Observations released by the UN Committee on the Rights of Persons with Disabilities in 2025. Participate in work and activities of the EU CRPD Monitoring Framework, including its potential revision.

Draft and submit information notes on European issues for the session of the CRPD Committee . 

	T 3.5
	Disability rights in Equality and Non-discrimination legislation
	Advocate for adoption an antidiscrimination legislation, and the upcoming new equality strategies post-2025 in collaboration with other non-discrimination NGOs such as AGE Platform Europe, ILGA Europe, ENAR, Equinet, ERGO Network, etc. 

Update EDF mapping of disability anti-discrimination legislation (from information from EDF 2019 human rights report)

	T 3.6
	Legal capacity and initiatives on the protection of adults
	Advocacy on EU’s promotion of supported-decision making and for compliance with the CRPD of the proposal for a Regulation on the protection of adults and ratification of the 2000 Hague Convention. 

	T 3.7
	Access to justice
	Ensure the perspectives and rights of persons with disabilities are mainstreamed in new and current initiatives related to access to justice, with a focus on victims’ rights (new victims’ rights strategy, participation in victims’ rights platform), anti-trafficking, and hate speech and hate crime. 



	
	Migration, including asylum and integration of migrants
	Advocate for the inclusion of migrants with disabilities in EU policies related to asylum and migrations. 

Contribute to the work of the advisory group of the EU Asylum Agency Vulnerability Experts Network (EDF became member in 2025) 

	T3.8
	Access to healthcare for persons with disabilities 
	Promote the EU guidelines on access to healthcare by persons with disabilities.

Advocate for access to healthcare for persons with disabilities in relevant EU initiatives. Continue the work on the European Framework on Health for persons with disabilities (WHO) as well as advocacy on mental health at the Council of Europe (campaign on the draft additional protocol to the Oviedo Convention and recommendations on voluntary measures). 

	T 3.10
	Gender equality and women with disabilities (in collaboration with the European Women’s Lobby and EIGE)
	Advocacy and promotion on the EU Gender Equality Strategy 2026-2030.  

Advocate for the ambitious transposition of a disability inclusive EU Directive on combatting violence against women and girls with disabilities, and contribute to the evaluation of the EU by the GREVIO on the Istanbul Convention. 

Campaign to prevent and end forced sterilisation against women and girls with disabilities in the EU and at national level.

Contribute to EIGE’s activities, including participation in its Gender Equality Forum 2026.

	T 3.11
	EDF Women’ Committee
	Activities and meetings of the EDF Women’s Committee. Work will include advocacy and awareness raising on the new EU Gender Equality Strategy, and future actions under the EU Disability rights strategy, as well as exchange on violence against women and ban of forced sterilisation. 

Selection of a new Committee following Board election. Training for new members. Adoption of a new workplan for 2027-2030. 

Participation in the work and activities of the European Womens’ Lobby, including the feminist economic working group and the observatory on violence against women 

	T 3.12
	Advocating for inclusive youth policies and initiatives
	Advocating for robust funding to support young persons with disabilities in the next MFF; Analysing and monitoring the implementation of EU youth policies, such as ERASMUS+ as part of the informal ERASMUS+ coalition, European Solidarity Corps, the revision of the Youth Guarantee, the Directive on Traineeships, etc.  

	T 3.13
	EDF Youth Committee
	Elect a new Youth Committee Organise activities and meetings of the EDF Youth Committee including participation in mainstream youth policy activities. Strengthen the engagement of youth in EDF’s work. Actively engage with the European Youth Forum and its activities as their member.


Work Package 4

	T4.1
	Contribute to the success of the ESRPD in its institutional set-up 
	Advocate for a second set of actions for the Disability Strategy 2025 – 2030; Participate in the Disability Platform and its events, meetings, and relevant sub-groups; Engage with all relevant institutions and bodies to advocate for the implementation of the ESRPD and the nomination of disability coordinators and their inter-institutional coordination; Participate in relevant actions of the AccessibleEU centre.

	T4.2
	European Disability Card and the EU Parking Card
	Advocate for inclusion and accessibility in the related delegated/implementing acts; continue advocacy for further legislation on freedom of movement. See also Activity T 2.8. 

	T4.3
	European Pillar of Social Rights (EPSR)


	Advocate for implementation of the EPSR and the new Social Pillar Action Plan; feed into all activities within the action plan relevant to persons with disabilities;  Disseminate the most recent data on the social inclusion pf persons with disabilities (particularly in employment) using Eurostat’s Disability Database,  explore the potential role of public procurement policies and the use of state aid in furthering the inclusion of persons with disabilities;  Participate in the Social Pillar Task Force within Social Platform and provide input to joint advocacy with other Social Platform members

	T 4.4
	European Semester and possible follow-up initiatives 


	Influence Semester Country Reports and Country-Specific Recommendations by giving input to Commission desk officers; Analyse recommendations and support EDF members in national advocacy towards implementation.

	T4.5
	Employment


	Provide policy proposals and support to the work of the European Commission in enhancing the meaningful employment of persons with disabilities in the EU in the open labour market through actions that will be integrated into the EU Strategy on the Rights of Persons with Disabilities; mainstream disability into  developments at the EU level on workers’ rights (in collaboration with the European Trade Union Confederation); Give input into changes to EU on public procurement and the use of state aid to promote the employment of persons with disabilities in the open labour market; continue advising EPSO and the EU institutions on how to foster better inclusion of workers with disabilities in the EU civil service.

	T4.6
	Social Protection


	Advocate for EU policies to ease the rise in costs of living. Advocate for policies at EU level to enable persons with disabilities to access social protection and services when moving between EU Member States for longer periods of time; Advocate for the use of personal budgets when providing funding for services for persons with disabilities; work to ensure the disability perspective is taken into account in the EU anti-poverty strategy

	T4.7
	Independent living and transition from institutional to community-based care 


	Advocate for strong clauses in the Regulations for Cohesion funding that will accelerate the transition from institutional to community-based care and independent living; work with European Expert Group on the Transition from institutional to community-based care (EEG). 

	T4.8
	Transport accessibility


	  Advocate for improvements in transport accessibility in all transport modes and all new relevant files.  Participate in European Railway Agency (ERA) meetings to revise the TSI-PRM and the Civil Aviation Conference (ECAC). 

	T4.9
	EU Passengers’ Rights


	Advocacy to influence the decision making procedures on the 2023 Passenger Rights Proposals with a focus on improving air passenger rights, and Regulation 261/2004 on air passenger rights in event of delays and cancellations. Provide input to the evaluation of Rail Passenger Rights Regulation. Gather and support disability related complaints on passenger rights. Actions to disseminate the results of the Human Rights Report on Air Travel. Collaboration with Age Platform Europe, BEUC and European Passenger Federation. 

	
	Accessible Housing and Cities
	2026 is the European Year of Cities. We will focus on urban mobility, housing, public buildings, and urban infrastructure to ensure that accessibility is taken into the account in, for example, the Affordable Housing Action Plan, the planning for the Sustainable Urban Mobility Plans (SUMPs), , the New European Bauhaus, or related European Standards. 

	T4.10
	Digital Single Market


	Provide policy recommendations regarding accessibility on EU policies in the digital domain, such as the Digital Euro and the Digital Wallet Regulations. Monitor developments and advocate for the implementation of specific accessibility legislation such as the European Accessibility Act, Web Accessibility Directive,Prepare and provide input to the upcoming evaluation / revision of the European Electronic Communications Code, and  Audiovisual Media Services Directive.

	T4.11
	A disability-inclusive Green Deal and Just Transition
	Influence opportunities in the follow-up to the EU Green Deal and the field of sustainability, amongst others through our work in the Just Transition Alliance. Represent persons with disabilities in relevant discussions both in their role as consumers and users as well as employees in policy fields related to transport, the built environment, energy, etc. 

	T4.12
	An accessible and inclusive European Standardisation System


	Bring the voice of the disability movement in relevant standardisation developments, such as the European Accessibility Act requested harmonised standards, as well as in advisory bodies and working groups together with ANEC (Representative organisation of consumers in standardisation), such as the European Commission Multi-Stakeholder Platform on Information and Communication Technology (ICT) Standards, and the key working groups inside the European Standards bodies (CEN, CENELEC, and ETSI) to promote mainstreaming of accessibility and inclusion of persons with disabilities. Provide policy recommendations for a more inclusive European Standardisation System (revision of Regulation 1025/2012).

	T4.13
	Global dimension of the European Disability Rights Strategy (and Articles 11 and 32 of the CRPD)


	Collaborate with the EU external services to ensure the implementation of international cooperation aspects of the ESRPD (chapter 6) including in the fields of international development and humanitarian action.


Work Package 5

	T5.1
	Annual communication plan
	Overall 2026 internal and external communication plan.

	T5.2
	Managing and updating the current EDF website and members area
	Keep website updated; updated page on the next EU Budget employment, passenger rights, accessibility, disability rights strategy amongst others. Creating and uploading news and blog articles.

	T.5.3
	Developing a new and improved EDF website
	Development of a new EDF website that incorporates accessibility, user interface and design  practices that cannot be improved in the current website, as well as enhances the experience for members through a new EDF intranet.

	T5.3
	Newsletters: Disability Voice, Women’s Voice, Global Action 
	Provide thematic information and reaching citizens with disabilities and allies through our newsletters; Women’s Voice, Global Action, Disability Voice newsletter on topics relevant to the disability community such as the situation on disability rights in at least one country holding the Presidency of the Council, Disability-inclusive cities, mental health, etc

	T5.4
	Social media campaigning 
	Continue to reach out and stay active. Channels include Twitter, Instagram, Facebook, LinkedIn and other emerging channels.

	T5.5 
	Disability rights in the news: Press and media 


	Connecting with press and media (both mainstream and disability specific), publish press releases, liaise with journalists.

	T5.6
	Top campaigns
	Including topics such as the next Multiannual Financial Framework, Passenger Rights, accessible citiesemployment, strengthening the Disability Rights Strategy. The campaigns will include offline promotional elements such as leaflets or stickers. 

	T5.7
	EDF Annual Report 2024
	Accessible annual report 

	T5.8 
	European Human Rights report  
	10th Human Rights Report on CRPD Monitoring Framework.

	T5.10
	European awards and competitions 
	Cooperate with the European Commission on the Access City Award, EDF Arts competition on future of disability, European Toy Manufacturers Awards (Empowerment Category). 

	T.5.11
	Internal communication 
	Members receive the weekly internal newsletter (“Re:Member”); analysis of use and readership of newsletter; Intranet developed and updated with relevant information for members, e.g. on governing bodies meetings. 


Work Package 6

	T6.1
	Ensuring a CRPD perspective in the international work of the next Multiannual Financial Framework (MFF) of the EU
	Advocate for a disability inclusive MFF in the relevant policy areas, including Neighbourhood, Development and International Cooperation Instrument, European Civil Protection and Humanitarian Aid Operations, Ukraine Facility, etc.

	T6.2
	Ensuring a global action dimension in the European Disability Rights Strategy (Articles 11 and 32 of the CRPD)

	Collaborate with the European External Action Service (EEAS), relevant DGs such as DG INTPA and DG ECHO, and EU delegations to ensure the implementation of international cooperation aspects of the ESRPD (chapter 6) including in the fields of international development, humanitarian action, preparedness, climate action, assistance and future reconstruction of Ukraine, disaster risk reduction.

	T6.3
	Ensuring a CRPD perspective and mainstreaming the rights of persons with disabilities in the EU External Action Plan on Human Rights and Democracy 
	Collaborate with the European External Action Service (EEAS), Human Rights and Democracy Network (HRDN) and EU delegations to ensure a disability inclusion in EU Human Rights Dialogues with partner countries. 

	T6.4
	Ensuring EU Official Development Assistance (ODA) projects are both mainstreaming persons with disabilities and targeting persons with disabilities
	Collaborate with EU institutions to increase the number of EU ODA projects that are inclusive of persons with disabilities. 

	T6.5
	Follow up and engage on regional and international events such as the European Humanitarian Forum, CoP31
	Several high-level events related to disability-inclusive development, humanitarian action and climate action will take place in 2026 and EDF will participate and follow up to ensure disability-inclusive development in the years to come. 


Work Package 7
	1
	Accessible Spaces For All: Improving Accessibility of Tourism for Persons with Disabilities in Central Europe ( 03/2023 to 02/2026)
	Improve governance and cooperation of multi-level cross-sectoral stakeholders for better territorial planning and implementation of accessible tourism for persons with disabilities in rural border regions in Central Europe.
	EDF
	Advisory board
	INTERREG Central Europe (EU)

	2
	AccessibleEU Centre (2023 – 2026)
	AccessibleEU is a resource centre on accessibility, working in the areas of built environment, transport, information and communication technologies, and accessibility policies, to ensure the participation of persons with disabilities in all areas of life on an equal basis with others.
	EDF
	Advisory board
	EU 

	3
	European disability expertise (2024-2027)
	The aim of EDE is to collect, analyse and provide independent scientific data and information relating to national policies and legislation, linked with provisions at EU level, as well as providing information about the situation of persons with disabilities.
	EDF,

Human European Consultancy
	Expert
	EU

	4
	“Empowered by AI” - AI for Accessibility, Inclusion and Rights of persons with disabilities (01/2025 – 12/2027)


	To solve the problem of lack of data on the topic of AI and disability EDF will conduct a research to identify the implications of AI on persons with disabilities.
	EDF
	COO
	Google.org

	5
	Nothing without us: Women with disabilities leading the change (12/2024 to 11/2027)
	Improvement in the inclusion and active participation of women with disabilities within the disability rights and feminist movements. This includes the establishment of women's committees, adoption and implementation of gender equality mainstreaming tools, and financial support for women's rights work at various levels.
	EDF lead
	COO
	Fondation Chanel

	6
	ACT4DYS-Enable people with disabilities and youth to act for sustainable cities- 2024-2026
	Project aims to build youth workers and young people's capacity in sustainable and inclusive urban development and empower them to take action to improve sustainability and inclusivity in urban communities.
	EDF as partner
	Partner
	Erasmus

	7
	Wellspring operating grant (until end of 2026/March 2027)
	Inclusion of persons with disabilities in the European Union's global work
	EDF as lead
	COO
	Wellspring Philanthropic Found


[image: image3.jpg]Avenue des Arts 7-8 Tel+3223290059 info@edf-feph.org
B1210 Brussels - Belgium Fax+322329 0059 www.edf-feph.org



1

